HEADLINES

- Work to convert the redundant warden’s house at The Lawns into two one-bedroom flats for elderly wheelchair users has been completed on programme and within budget. As well as increasing our stock of smaller homes, the new flats will produce an annual rental income of £7,100.

- Tenders have now been invited to reinstate curb edgings and resurface footpaths and access roads at Windsor Gardens. Work is due to start in November 2013.

Notes

Spend shows the position as at 7th October 2013

| Cost Centre | Project | Budget £ |
| --- | --- | --- |
| H420 | Improving Access for Disabled People | 458,000 |
| H430 | Decent Homes – Electrical Upgrades | 208,000 |
| H435 | Decent Homes - Kitchen & Bathroom Renewal | 318,000 |
| H440 | Door Entry Systems | 50,000 |
| H441 | Decent Homes - Window Renewal | 146,000 |
| H442 | Decent Homes - Central Heating | 297,000 |
| H443 | Decent Homes – Re-Roofing | 250,000 |
| H445 | Decent Homes – External Wall Repairs | 40,000 |
| H446 | Composite Door Replacements | 214,000 |
| H447 | Major Voids | 350,000 |
| H448 | Structural Improvements | 164,000 |
| H449 | External Wall Insulation | 110,000 |
| H450 | Environmental Improvements - Highfields | 40,000 |
| H455 | Decent Homes - Replace Oil Tanks | 38,000 |
| H456 | Decent Homes - Fire Precautions (Fire Doors) | 70,000 |
| H457 | Decent Homes - Other Works | 40,000 |
| H458 | Loft and Internal Wall Insulation | 29,000 |
| H459 | Sheltered Housing – External Area Enhancements | 45,000 |
| H460 | Conversion of Wardens Flat | 60,000 |
| H461 | Refurbishment - Hampden Crescent | 150,000 |
| H462 | Decent Homes - Fire Precautions | 108,000 |
| H463 | Homes for the Future | 75,000 |
| TOTAL |  | 3,260,000 |

| Cost centre | H440 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Door Entry Systems |  |  |  |  |  |  |
| Description | A rolling programme to install door entry systems to blocks of flats |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 169 |
| Budget | £50,000 | Spend |  | £26,549 | Projection |  | £50,000 |
| Contractor | Entrotec |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Jan-13 |  |  | - |  |
|  | Sketch scheme |  | Feb-13 |  |  | - |  |
|  | Tender approval |  | N/A |  |  | - |  |
|  | Start on site |  | Aug-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | 1 block completed. 9 further blocks to be completed and 18 programming units to be upgraded by year end. |  |  |  |  |  |  |

| Cost centre | H441 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Window Renewal |  |  |  |  |  |  |
| Description | A rolling programme for the installation of replacement UPVC windows. |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 32 |
| Budget | £146,000 | Spend |  | £44,133 | Projection |  | £76,000 |
| Contractor | Astraseal |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | Dec-12 |  |  | - |  |
|  | Tender approval |  | Apr-13 |  |  | - |  |
|  | Start on site |  | May-13 |  |  | - |  |
|  | Completion |  | Dec-13 |  |  | - |  |
| Comments | St Andrews Court and Spring Gardens are complete. Further works at Yeomans Court are to be tendered, with a view to completion within budget this year. |  |  |  |  |  |  |

| Cost centre | H443 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Roof Renewal |  |  |  |  |  |  |
| Description | Replacement of existing tiled roofing to various properties throughout the Borough |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 55 |
| Budget | £250,000 | Spend |  | £15,438 | Projection |  | £220,000 |
| Contractor | Warkton Roofing |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | May-13 |  |  | - |  |
|  | Start on site |  | Aug-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Work commenced in August. 7 properties now completed. On target to complete all 55 units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H447 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Void Repairs and Improvements |  |  |  |  |  |  |
| Description | Major repair works to void properties |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 50 |
| Budget | £350,000 | Spend |  | £194,001 | Projection |  | £350,000 |
| Contractor | A L Holland |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | Jun-10 |  |  | - |  |
|  | Start on site |  | Apr-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Works completed to 15 properties. On target to complete 50 units by year end and on budget. |  |  |  |  |  |  |

| Cost centre | H448 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Structural Improvements |  |  |  |  |  |  |
| Description | Ad hoc underpinning and damp proofing works identified through surveys |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 82 |
| Budget | £164,000 | Spend |  | £85,178 | Projection |  | £164,000 |
| Contractor | Various |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | N/A |  |  | - |  |
|  | Start on site |  | Apr-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Works completed to 17 properties. On target to complete 82 units on budget by year end. |  |  |  |  |  |  |

| Cost centre | H449 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | External Insulation |  |  |  |  |  |  |
| Description | Installation of external wall insulation on properties without mains gas where construction does not permit installation of cavity wall insulation |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 16 |
| Budget | £110,000 | Spend |  | £25,671 | Projection |  | £95,000 |
| Contractor | Goldsmith and Son |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Feb-13 |  |  | - |  |
|  | Sketch scheme |  | Apr-13 |  |  | - |  |
|  | Tender approval |  | May-13 |  |  | - |  |
|  | Start on site |  | Jul-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Works completed to 8 properties. Grant funding of £39,000 from Scottish Power has been obtained under the ECO scheme. On target to complete 16 units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H450 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Environmental improvements – Highfield Road Estate |  |  |  |  |  |  |
| Description | New recycling and bin areas to three blocks on Highfield Road Estate |  |  |  |  |  |  |
| Status | Feasibility Study |  |  |  | Units |  | 18 |
| Budget | £40,000 | Spend |  | £0 | Projection |  | £45,000 |
| Contractor | N/A |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Feb-13 |  |  | - |  |
|  | Sketch scheme |  | Mar-13 |  |  | - |  |
|  | Tender approval |  | Dec-13 |  |  | - |  |
|  | Start on site |  | Feb-14 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Tenant consultation exercise undertaken in August and September |  |  |  |  |  |  |

| Cost centre | H456 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes- Fire Precautions |  |  |  |  |  |  |
| Description | Replacement of timber fire doors in flats with GRP doors |  |  |  |  |  |  |
| Status | Tender stage |  |  |  | Units |  | 72 |
| Budget | £70,000 | Spend |  | £4,483 | Projection |  | £54,000 |
| Contractor | Permador |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Sep-12 |  |  | - |  |
|  | Sketch scheme |  | Nov-12 |  |  | - |  |
|  | Tender approval |  | May-13 |  |  | - |  |
|  | Start on site |  | Nov-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Tender awarded for £54,000. Work to commence on-site in Nov 2013. On target to complete 72 units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H457 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes – Other Works |  |  |  |  |  |  |
| Description | Works to address properties identified as potentially non-decent during 2013 |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 4 |
| Budget | £40,000 | Spend |  | £28,624 | Projection |  | £40,000 |
| Contractor | A L Holland |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Feb-13 |  |  | - |  |
|  | Sketch scheme |  | May-13 |  |  | - |  |
|  | Tender approval |  | Jul-13 |  |  | - |  |
|  | Start on site |  | Aug-13 |  |  | - |  |
|  | Completion |  | Mar-13 |  |  | - |  |
| Comments | Two properties completed to date. On target to complete all four units on budget by year end. |  |  |  |  |  |  |

| Cost centre | H458 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Internal Wall Insulation |  |  |  |  |  |  |
| Description | Provision of wall and loft insulation to increase energy efficiency |  |  |  |  |  |  |
| Status | Complete |  |  |  | Units |  | 30 |
| Budget | £29,000 | Spend |  | £9,802 | Projection |  | £9,802 |
| Contractor | SIG Energy Management |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | N/A |  |  | - |  |
|  | Start on site |  | N/A |  |  | - |  |
|  | Completion |  | N/A |  |  | - |  |
| Comments | All work was completed in 2012/13.A payment was made at the beginning of 2013/14 for work completed in 2012/13. Remaining budget is to be reallocated. |  |  |  |  |  |  |

| Cost centre | H459 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Car Park Enhancements |  |  |  |  |  |  |
| Description | Resurfacing and repairs to various garage areas and sheltered housing car parks throughout the Borough |  |  |  |  |  |  |
| Status | Tender stage |  |  |  | Units |  | 74 |
| Budget | £45,000 | Spend |  | £345 | Projection |  | £45,000 |
| Contractor | N/A |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Aug-13 |  |  | - |  |
|  | Sketch scheme |  | Sep-13 |  |  | - |  |
|  | Tender approval |  | Oct-13 |  |  | - |  |
|  | Start on site |  | Nov-13 |  |  | - |  |
|  | Completion |  | Dec-13 |  |  | - |  |
| Comments | Works are currently out to tender for Windsor Gardens. Tender opening will be on 21 October. |  |  |  |  |  |  |

| Cost centre | H460 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Conversion of Warden’s House |  |  |  |  |  |  |
| Description | Conversion of warden’s house at the Lawns sheltered housing scheme to provide two one-bedroom flats for wheelchair users. |  |  |  |  |  |  |
| Status | Complete |  |  |  | Units |  | 2 |
| Budget | £60,000 | Spend |  | £51,189 | Projection |  | £51,189 |
| Contractor | Boothville Roofing |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | 2011 |  |  | - |  |
|  | Sketch scheme |  | Feb-13 |  |  | - |  |
|  | Tender approval |  | Mar-13 |  |  | - |  |
|  | Start on site |  | Apr-13 |  |  | - |  |
|  | Completion |  | Sep-13 |  |  | - |  |
| Comments | Work completed in September 2013 – on programme and £12,000 below budget |  |  |  |  |  |  |

| Cost centre | H461 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Hampden Crescent – Regeneration |  |  |  |  |  |  |
| Description | Refurbishment of Hampden Crescent flats and environmental improvements |  |  |  |  |  |  |
| Status | Feasibility stage |  |  |  | Units |  |  |
| Budget | £150,000 | Spend |  | £0 | Projection |  | £150,000 |
| Contractor | N/A |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | May -12 |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | N/A |  |  | - |  |
|  | Start on site |  | N/A |  |  | - |  |
|  | Completion |  | N/A |  |  | - |  |
| Comments | Designs prepared and circulated to tenants in September |  |  |  |  |  |  |

| Cost centre | H462 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes – Fire Precautions |  |  |  |  |  |  |
| Description | Various remedial works identified during fire risk assessments |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  |  |
| Budget | £108,000 | Spend |  | £17,922 | Projection |  | £108,000 |
| Contractor | Smith Fire |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | Jul-11 |  |  | - |  |
|  | Sketch scheme |  | Sep-11 |  |  | - |  |
|  | Tender approval |  | Mar-13 |  |  | - |  |
|  | Start on site |  | May-13 |  |  | - |  |
|  | Completion |  | Mar-14 |  |  | - |  |
| Comments | Stage 1 (Barnes Close and Whiteford Drive) complete Stage 2 (George Street and Saunders Close) commenced Sep 13 and due for completion in October. Tenders are out for Stage 3 (The Lawns). |  |  |  |  |  |  |

| Cost centre | H463 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Homes for the Future |  |  |  |  |  |  |
| Description | Full refurbishment of pre-1945 properties to provide modern amenities, enhanced energy efficiency and a thirty year life free of major maintenance works |  |  |  |  |  |  |
| Status | Feasibility stage |  |  |  | Units |  |  |
| Budget | £75,000 | Spend |  | £0 | Projection |  | £75,000 |
| Contractor | N/A |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  | N/A |  |  | - |  |
|  | Sketch scheme |  | N/A |  |  | - |  |
|  | Tender approval |  | N/A |  |  | - |  |
|  | Start on site |  | N/A |  |  | - |  |
|  | Completion |  | N/A |  |  | - |  |
| Comments | Project on hold pending approval of ‘Homes for the Future’ proposals |  |  |  |  |  |  |

| Cost centre | H420 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Improving Access for Disabled People |  |  |  |  |  |  |
| Description | Installation of aids and adaptations to council housing across the Borough |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 65 |
| Budget | £458,000 | Spend |  | £112,200 | Projection |  | £458,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | On target to complete all 65 units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H430 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes – Electrical Upgrades |  |  |  |  |  |  |
| Description | Rolling programme to upgrade electrical installations |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 89 |
| Budget | £208,000 | Spend |  | £65,000 | Projection |  | £208,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | On target to complete all units within budget by year end |  |  |  |  |  |  |

| Cost centre | H435 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Kitchen and bathroom renewal |  |  |  |  |  |  |
| Description | Rolling programme of kitchens and bathroom refurbishment |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 32 |
| Budget | £318,000 | Spend |  | £195,000 | Projection |  | £318,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | On target to complete all units within budget by year end |  |  |  |  |  |  |

| Cost centre | H442 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Central Heating Upgrades |  |  |  |  |  |  |
| Description | Rolling programme of central heating boiler replacement |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 156 |
| Budget | £297,000 | Spend |  | £107,000 | Projection |  | £297,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | On target to complete all units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H445 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes – External Wall Repairs |  |  |  |  |  |  |
| Description | Brickwork repairs to various properties in Desborough |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 30 |
| Budget | £40,000 | Spend |  | £27,000 | Projection |  | £40,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | Programme fell behind last month due to weather, but will catch up and complete all units on budget by year end. |  |  |  |  |  |  |

| Cost centre | H446 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | External Doors |  |  |  |  |  |  |
| Description | Rolling programme of external door replacements |  |  |  |  |  |  |
| Status | On-site |  |  |  | Units |  | 256 |
| Budget | £214,000 | Spend |  | £130,000 | Projection |  | £214,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | On target to complete all units within budget by year end. |  |  |  |  |  |  |

| Cost centre | H455 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project name | Decent Homes – Replace Oil Tanks |  |  |  |  |  |  |
| Description | Replacement of central heating oil tanks in rural properties |  |  |  |  |  |  |
| Status | Complete |  |  |  | Units |  | 12 |
| Budget | £38,000 | Spend |  | £18,000 | Projection |  | £38,000 |
| Contractor | KBC Environmental Care |  |  |  |  |  |  |
| Programme |  |  | Now |  |  | Last |  |
|  | Brief |  |  |  |  | - |  |
|  | Sketch scheme |  |  |  |  | - |  |
|  | Tender approval |  |  |  |  | - |  |
|  | Start on site |  |  |  |  | - |  |
|  | Completion |  |  |  |  | - |  |
| Comments | Completed all units in initial programme. 13 extra properties have been added to the programme for completion within budget by year end. |  |  |  |  |  |  |