BOROUGH OF KETTERING

EAST KETTERING LIAISON FORUM

MEETING HELD: 19th June 2014

Present :	Councillor Lloyd Bunday (Chair)

Councillors Christopher Lamb, Ruth Groome, Philip Hollobone and Shirley Lynch (Kettering Borough Council), Councillors Victoria Lamb (Warkton Parish Council) and Toni Wilkin (Weekley Parish Council), Alan Wordie (Alledge Brook LLP), Dr Tom Kelly (CPRE) and Cayti Bilski (Churches Together)

Also Present:	Nine members of the public.

KBC Officers : 	Martin Hammond, Adrian Arnold, Serena Penny and Rob Harbour

Rachel Paling (Committee Administrator)

NCC Officers : 	None

Members of the Press : 	 None

Apologies : 	Cllrs Russell Roberts, Eileen Hales MBE, Linda Adams (Kettering Borough Council), Cllr Christopher Groome (NCC), Cllr Jim Harker (NCC), Cllr Allan Matthews (NCC), Cllr Stephen Pickard (Cranford PC), Cllr Reg Barby (Barton Seagrave PC), Insp Richard Tall (Police), Kaarin Goodburn (PFAG) and Bill Warden (Hallam Land), Richard Hall (NCC Highways)

| REF | Item / Issue | Response/Action | Responsibility | Timescale |
| --- | --- | --- | --- | --- |
| 14.EKLF.01 | NOTES OF MEETING HELD ON 24th APRIL 2014 The notes of the last meeting held on 24th April 2014 were agreed by the members of the forum as a true record of the meeting. |  |  |  |
| 14.EKLF.02 | ACTIONS ARISING FROM THE NOTES OF THE LAST MEETING 13.EKLF.52 pg 6 – ‘A link to the technical document’ | This was still to be received by Dr Tom Kelly (Subsequently re-sent) | Adrian Arnold |  |
| 14.EKLF.03 | UPDATES A presentation was given to the forum. Timeline for Delivery and Action Plan:- An updated timeline with delayed start dates and an updated Route Map was circulated. It was noted that the Variation of Condition Application 2 would be submitted to the Planning Committee for approval on 8th July 2014. Further East Kettering applications would be submitted to Planning Committees set for 4th or 9th September and 7th or 14th October 2014. Alan Wordie reported that the simplification of Tranche 1 had been completed. Infrastructure funding was now in place with HCA (Homes and Communities Agency) and it was hoped that within a week the Primary School funding would also be in place. In respect of the Attenuation Basin, the newts were to be moved to new water and then work could possibly be started on site in August or September 2014. Work on Access D was also due to commence as soon as the S106 Agreement had been signed. The works to access junctions and access roads was being planned so as to minimise disruption to existing highway space; with junction F likely to start before junction E; construction access to the school would come off Cranford Rd. Access F would be completed by September 2015 The developer was seeking forward funding from the government for the road linking access roads E and F and which would also serve the new primary school, and district centre, for delivery in 2015. Planning Applications:- Primary School The PS4 school was scheduled to be open for September 2015. The planning application was due to go to the Planning Committee on 23rd July 2014. A temporary drop-off facility would be in place for the opening of the school. Variation of Condition Application 2 (VOC2) The VOC2 seeks to: Vary the Strategic Master Plan, Phasing Plans and Land Use Schedule Amend the phased approach from 3 Phases of development to 2 Phases Amend the trigger point from 1750 to 2700 dwellings for the conditions requiring highway improvements at junctions 10 and 10A Amend the 300 dwellings review trigger to 375 The housing built would help to pay back the forward funding. Junction 10 would be upgraded to cope with the extra traffic until the number of occupied dwellings reached 2700. The Hallam Variation of Conditions were :- Condition 18 – Code for Sustainable Homes Condition 19 – Lifetime Homes Condition 22 – Interim Design Stage Assessment Cert. Condition 42 – Access to A14 (300) Condition 45 – Removal of road improvements (c) Deeble Road/Windmill Ave : now covered by Hallam draft S106 Pre-Commencement of Conditions Strategic Landscaping was due to start in the summer months. Residential Applications The Taylor Wimpey application was to be changed to Reserved Matters and would be submitted to the Planning Department soon. A consultation process would then commence. Persimmon Homes had now signed up to the AWA strategic drainage position along with the other builders and therefore no longer needed an on-site balancing pond. Surface water would be channelled to the strategic drainage. Infrastructure Junction 10/10a Business Case A business case had been submitted to government but a timetable for a decision had not been made. Work was still on-going with SEMLEP and NEP. The Roxhill application for a business park south of the A14 near junction 10 was due to go to Planning Committee on 23rd July 2014. Consultation and Engagement Work A newsletter was being prepared and would be distributed in August, after July committee decisions. |  |  |  |
| 14.EKLF.04 | QUESTIONS ON UPDATES Q Would Access D, E and F need to be completed before houses could be built? Q How will the foul water get off-site? Q Will there be traffic calming in Cranford before the works start on Access F? Q Are there any plans for Cranford School? Q What type of school will the PS4 school be? Q Will residents on Warkton Lane (including the service road) be kept updated on the progress and any consultations of Access D? Q Will residents get extra time for consultation as the summer holiday period was approaching? Q Will Persimmon homes be in keeping with current properties? Q Will there be a problem in selling the houses? Q Is there a precise route for the WeWaA? Q What improvements to other roads will take place to accommodate the significant increases in vehicles, until the trigger point of 2700 is reached for J10a to be implemented? | A The first houses would be built as Access D was constructed. However, the houses cannot be occupied until Access D was complete. These first houses did not depend on E and F being completed. A In the short term, the water would go to a holding tank and would then be emptied accordingly. Long term, the water will be taken to the east of Burton Latimer. A The NCC were aware of the situation and there was money from S106 to fund the issue in relation to construction traffic using existing roads. The traffic calming works would be funded and therefore provided during the first phase of development A The diocese were confident they would keep numbers at the village school at a viable level. A The PS4 school will be a Church of England Academy. A KBC will ensure the residents get updated by NCC Highways. A The consultation period would be extended for as long as it was possible. A The Design Code dictates how the homes should be built including density, relationship to existing properties, layout and appearance and therefore there would a blend from existing houses and the new properties adjacent to them. A The risk of selling houses lies with the developer, and it was now practice for developers to build houses only when they were sure of sales. The development will also bring £20million of funding to improve the town centre, which amongst other things, would help sell Kettering as a place to live. A There is a suggested route in the Master Plan, however further work is needed to clarify if this is the best exact route and the costs involved. A Improvements to J10 of the A14 will be brought forward to help with the increase in traffic as well as wider infrastructure. | Adrian Arnold to contact NCC Highways to request updates to be sent. |  |
| 14.EKLF.05 | PUBLIC QUESTION AND ANSWER SESSION Q Are all the alterations to junctions being funded by the development? Q How will there be four lanes at the Windmill Avenue/Barton Road junction? | A Yes, through S106 agreements and NCC Highways will carry out that work. A There was an on-going piece of work being completed by NCC Highways to consider the options for this junction. |  |  |
| 14.EKLF.06 | ITEMS FOR NEXT MEETING No items submitted |  |  |  |
| 14.EKLF.07 | DATE OF NEXT MEETING 30th September 2014 |  |  |  |

(The meeting started at 6.00 pm and ended at 7.20 pm)

Signed …………………………………………………………………………………………………

Chair