BOROUGH OF KETTERING

EAST KETTERING LIAISON FORUM

MEETING HELD: 30th September 2014

Present :	Councillor Lloyd Bunday (Chair)

Councillors Christopher Lamb, Eileen Hales MBE, Derek Zanger and Shirley Lynch (Kettering Borough Council), Councillors Victoria Lamb (Warkton Parish Council), Reg Barby (Barton Seagrave PC), Stephen Pickard (Cranford PC), Fergus MacDonald (Burton Latimer TC), and Toni Wilkin (Weekley Parish Council), Cllr Christopher Groome (NCC), Cllr Jim Harker (NCC), Alan Wordie (Alledge Brook LLP), Daniel Oladejo (Environment Agency), Dr Tom Kelly (CPRE), Bill Warden (Hallam Land) and Cayti Bilski (Churches Together)

Also Present:	Fourteen members of the public.

KBC Officers : 	Martin Hammond, Adrian Arnold, Louise Holland, Serena Penny and Rob Harbour

Rachel Paling (Committee Administrator)

NCC Officers : 	Richard Hall (NCC Highways)

Members of the Press : 	 None

Apologies : 	 Cllr Russell Roberts, Cllr Philip Hollobone, Cllr Allan Matthews (NCC) and Insp Richard Tall (Police).

| REF | Item / Issue | Response/Action | Responsibility | Timescale |
| --- | --- | --- | --- | --- |
| 14.EKLF.08 | NOTES OF MEETING HELD ON 19th JUNE 2014 The notes of the last meeting held on 19th June 2014 were agreed by the members of the forum as a true record of the meeting. |  |  |  |
| 14.EKLF.09 | ACTIONS ARISING FROM THE NOTES OF THE LAST MEETING 14.EKLF.03 pg 5 – Infrastructure, J10/10a Business Case | A bid had been submitted to Government, showing draft costings and route connections to the A6, as well as a Risk Management Assessment to show it is a viable junction. There was as yet no certainty about the junction being funded, and the purpose of the business case was to establish that it merited funding by government, in whole or in part. At the point that the junction was funded, work would start on design, and consultation would follow. |  |  |
| 14.EKLF.10 | UPDATES A presentation was given to the forum. - Timeline for Delivery and Action Plan:- An updated timeline and Route Map were circulated. Funding was now in place for Access E&F, surface water drainage and the primary school (PS4). The consultation period for the primary school (PS4) was due to finish on 2nd October 2014. The design of the central road between Access E & F was due to be finished shortly and then a planning application would be submitted. Alan Wordie advised that the work on Access points D, E and F would be staggered. It was expected construction vehicles would be able to get on site for Access D by mid-late October 2014. Work on Access F was due to start in January 2015 and Access E in February 2015. Cranford Road would be crossed by Access F. - Planning Applications:- Primary School Pre-commencement details had been finalised. The PS4 school was still on schedule to be open for September 2015, although the timetable remained challenging. Some work would begin on site within a few days. Residential Applications Taylor Wimpey had submitted a Reserved Matters application for Parcel 19 of the development. - Application was for 167 dwellings, access roads, landscaping, drainage and other enabling works. - Consultation was underway. Awaiting a number of statutory consultee responses. - Issues relating to drainage and design were currently being assessed. Local objections were being considered. The developer had been made aware of these. Taylor Wimpey had also submitted a Variation of Conditions application. The application sought to vary Condition 18 and 19 of the outline planning permission for Parcel R19 only. - Condition 18 related to the Code Level for Sustainable Homes (currently required all dwellings completed between 1 Jan 2013 to 31 Dec 2015 to achieve Code Level 4 and Code 6 thereafter). - Condition 19 related to the provision of lifetime homes standards (currently required all properties to achieve this standard). There were on-going discussions with the developers to improve the Code level performance of the houses above the level they had submitted. - Infrastructure Strategic Landscape The strategic drainage on-site had been approved. A more detailed survey was required around Burton Latimer in relation to off-site works. Health Discussions had started with NHS, Nene Commissioning Group and local practices in respect of health options. | More information would be brought to a future meeting once available. Further information would not be available until Mar/Apr 2015. | Adrian Arnold |  |
| 14.EKLF.11 | QUESTIONS ON UPDATES Q Has the position of the access road in Warkton Lane been decided? Q In relation to the modelling exercise of Barton Road/Warkton Lane junction, how will it cope with further developments too in Burton Latimer, as it is already struggling with increased traffic? Q Can the traffic calming and landscaping in Cranford be brought forward? Q When will the strategic drainage be built in relation to Burton Latimer? Q What access will Anglian Water Authority have in relation to the field at Poplars Farm Road and drainage? Q When will street planting take place as trees need time to grow? | A A consultation had taken place on the proposal for the centre option onto the service road for committee, which considered the views and approved the position on to Warkton Lane. A safety audit was now taking place by NCC Highways and no issues were raised by them. A Apart from the improvements planned for this junction, there was also a commitment and funding available to improve other sections and junctions along Barton Road, London Road and Windmill Avenue. All these junctions would be considered as a whole rather than each one being dealt with separately. A feasibility study on detailed solutions for the Windmill Ave/Barton Rd junction had been commenced. There was money in the S106 for works to this junction. There were also plans for traffic schemes by the county council relating to the town centre which would have a positive effect on traffic flow through Kettering. A It was intended that traffic calming in Cranford would be one of the early schemes being funded from the roof charge receipts. Cllr Jim Harker (NCC) confirmed that planting on Cranford Road and Grafton Road was planned for Autumn 2014. A A survey was to be completed along with a feasibility report and once these had been completed, it was hoped a timeline could be agreed with Anglian Water Authority. A AWA will have to work within an existing easement. Taylor Wimpey were also aware of the issues and situation, as these had been raised during the planning application’s consideration. A The street planting formed part of the development process. Access D would commence soon after December 2014. Some landscaping maybe put in autumn 2015. KBC would attempt to retrieve a more precise timeline from the developer with reference to open space. |  |  |
| 14.EKLF.12 | PUBLIC QUESTION AND ANSWER SESSION Q What is the situation regarding the junctions of Windmill Avenue, Barton Rd and Pytchley Road? Q What restraints have been incorporated into Construction Traffic Management Plans to ensure delivery times do not inconvenience people? Q Will there be safe access through the school? Other Comments It was noted that funding comes to fruition once the development has started. It was in the nature of large scale developments that developers would seek to change elements of the plans as they proceeded, and these discussions required the Council to balance the aspirations of the original plans with the need to make the development viable, and to progress housing delivery. Nevertheless, there have been positive developments as a result of involving government departments who had the ability to provide forward funding in a way which brought forward infrastructure and facilities ahead of which the development would produce “naturally” and for example, the primary school was being provided some two years earlier than had originally been expected and the district centre was now likely to appear several years ahead of the original trajectory. Cllr Christopher Lamb advised that Barton Seagrave Parish Council would liaise with the Contracts Manager on any concerns around the primary school. | A Funds had been secured from the developer. A meeting with design strategists would be held in a few weeks. An update would be given at the December meeting. A This formed part of a pre-commencement plan and the conditions that had been discharged were available on the council’s website. A The intention is to use Access E and then seek further funding for a joining road from the end of Access E. | Richard Hall | 4th December 2014 |
| 14.EKLF.13 | ITEMS FOR NEXT MEETING No items submitted except those detailed above. |  |  |  |
| 14.EKLF.14 | DATE OF NEXT MEETING 4th December 2014 |  |  |  |

(The meeting started at 6.00 pm and ended at 7.20 pm)

Signed …………………………………………………………………………………………………

Chair