## Sheet1
East Kettering | [6 empty] | 2015 | [11 empty] | 2016
Work - stream | Description | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July
Planning | bar: August to 2015 December
| s106 (Hallam, Taylor Wimpey & Persimmon) | August: ABL s106 complete s106 Hallam &TW almost; Persimmon in discussion; November: target to conclude
| Final pre development conditions | August: all complete; October: all pre development conditions discharged
| Specific detailed condition discharge pre development | September: By house builder on individual parcels
F | RMA (Infrastructure) Access D | September: RMA and AOC approved; October: see delivery
A | RMA (I) attenuation for 1st dwellings | September: RMA approved; October: see delivery
B | RMA (I) Access E plus 500m road | September: RMA and AOC approved; October: see delivery
B+ | RMA (I) road from central park to school (& Cranford Rd to school) | September: detailed design and planning; October: planning submission; December: planning committee; 2015 January: delivery May to June & July to September 2015
C | RMA Access F plus 1,000m road | September: RMA and AOC approved; October: see delivery
D | RMA (I) PS4 (first primary school) | September: Consultation to 2nd October; October: see delivery
E | RMA FW (By AWSL) | September: Design completion; October: planning submission; November: committee; December: see delivery
F | RMA DWH/Barratt (R7, R9, R10) | September: RMA approved; October: see delivery
G | RMA Persimmon(R23 & R26) | August: RMA ongoing design; September: S106; October: committee date??; November: delivery
H | RMA TW (R19) | August: RMA submission; October: RMA committee??; November: Land drawdown; 2015 February: Infrastructure delivery; 2015 April: delivery
J | RMA ABL (R20, R24, E3, DC2) | September: RMA approved; October: delivery
Delivery | bar: August to 2015 December
A | Attenuation Basin | October: s104 tech approval and agreement; November: 01/11/14 contract commence 16 weeks; 2015 February: surface water solution available 28/02/2015
B | Access E and 500 m road | August: Prelims and Preparation; October: s278/s38; December: Christmas Break; 2015 January: Access E works; 2015 March: R19 access; 2015 April: R20 access; 2015 May: delivery
B | 250 m road through to Central Bowl | 2015 March: 250m road (18 weeks); 2015 May: DC2 access; 2015 July: Central Park accessed; 2015 August: delivery
B+ | Central Bowl to school | 2015 June: Central Park to school; 2015 July: programme contingency; 2015 August: delivery
C | Access F and 300 m road | September: Prelim & prep; October: S278/S38; December: Christmas Break; 2015 January: Access F works; 2015 March: R24 access; 2015 April: E3 access; 2015 May: delivery
C | next 600m road | 2015 March: s38 road (28 weeks); 2015 May: R23 access; 2015 August: delivery
B+ | Cranford Rd to school | 2015 July: Cranford Rd to school; 2015 September: Link road completed
D | School PS4 | September: Enabling Works; October: Construction of PS4 school and playing fields; 2015 July: contingency period; 2015 August: snagging; 2015 September: PS 4 available for 01/09/15
E | Foul Water strategic sol'n | December: strategic main upgrade
F | Access D and roads | October: DWH commence roads; November: R7, R9, R10 access; 2015 January: delivery
F | DWH house building | November: DWH house building; 2015 March: attenuation available; 2015 April: occupation
G, H & J | Other house builders commence | 2015 January: Potential Persimmon start; 2015 March: Potential TW start; 2015 May: Potential R24 start
Next stages | bar: August to 2015 December
K | Distict Centre | September: Branding; November: marketing of DC; 2015 March: legals; 2015 July: DC2 access; 2015 August: DC2 delivery; 2016 March: delivery to benefit from link road New Year opening!
K |  | 2015 April: RMA DC2 pt; 2015 August: committee?????
L |  | 2015 August: marketing private health and care at DC1with benefit of link access; 2015 December: legals
L |  | 2015 October: RMA DC 1 or 2 pt; 2016 January: committee
Pump Prime Loan Funding | bar: August to 2015 December
C | SEMLEP | September: infrastructure contract agreed with SEMLEP; October: draw SEMLEP for Access F works
C | NEP | December: Forecast Infrastructure contract agreed with NEP; 2015 January: draw NEP for southern road works in conjunction with SEMLEP funderd roads at Access F
B+ | HCA LSIP | 2015 May: draw LSIP to deliver link road between Central Bowl and school; 2015 July: draw LSIP to deliver link road between Cranford Road & school
D | HCA LIF school | September: infrastructure contract agreed with HCA; October: draw for school
A&B | HCA LIF non school | September: infrastructure contract agreed with HCA; December: draw funding for Attenuation/SUDS Access E and road to central bowl
NOTES:
|  | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January |  | February | April | May | June | July
[7 empty] | 2015 | [11 empty] | 2016
CURRENT DATE