## Sheet1
Neighbourhood Management
Timeline for submission of Environmental Schemes 2015/2016
When By | Activity | Who
March/April 2015 | Identification of proposed schemes and estimated costs (also discussed at individual 1-1s) | Neighbourhood Manager (discussed with Neighbourhood Services Manager)
May-June 2015 | Consultation with tenants and leaseholders affected /firm costings obtained | Neighbourhood Manager
2015-07-01 | Submit schemes for consideration/approval to Tenancy Services Manager/Neighbourhood Services Manager- and volunteers from Tenants Forum Representatives | Neighbourhood Manager - approval by TSM/NSM/TF
2015-08-01 | Determine start and finish dates via contractors /prepare article for September edition of CONNECT | Neighbourhood Manager/Neighbourhood Services Manager
2015-09-01 | Start on site no later than September 2013 | Neighbourhood Managers to monitor
October/February 2015 | Regular monthly review of progress per scheme any potential slippage to be reported to HMT | Neighbourhood Services Manager
2015-03-01 | Completion of schemes /quality checks carried out | Neighbourhood Manager
2015-04-01 | Survey tenants/leaseholders on satisfaction with schemes | Neighbourhood Manager