BOROUGH OF KETTERING

EAST KETTERING LIAISON FORUM

MEETING HELD: 24th March 2015

Present :	Councillor Lloyd Bunday (Chair)

Councillors Russell Roberts, Jonathan Bullock, Mark Dearing, Derek Zanger, Shirley Lynch, Christopher Lamb, Cllr Eileen Hales MBE, Linda Adams, Victoria Lamb (Warkton Parish Council), Reg Barby (Barton Seagrave PC), Stephen Pickard (Cranford PC), Fergus MacDonald (Burton Latimer TC) and Toni Wilkin (Weekley Parish Council) and Dr Tom Kelly (CPRE).

Also Present:	Twenty-one members of the public.

KBC Officers : 	Adrian Arnold, Louise Jelley, Ruth James, Nicola Thompson and Rob Harbour

Rachel Paling (Committee Administrator)

NCC Officers : 	Richard Hall (NCC Highways)

Members of the Press : 	None

Apologies : 	Cllr Ruth Groome, Cllr Philip Hollobone, Cllr Christopher Groome (NCC), Cayti Bilski (Churches Together), Sgt Scott Little (Police), Bill Warden (Hallam Land) and Alan Wordie (Alledge Brook LLP).

| REF | Item / Issue | Response/Action | Responsibility | Timescale |
| --- | --- | --- | --- | --- |
| 14.EKLF.22 | NOTES OF MEETING HELD ON 4TH DECEMBER 2014 The notes of the last meeting held on 4th December 2014 were agreed by the members of the forum as a true record of the meeting. |  |  |  |
| 14.EKLF.23 | ACTIONS ARISING FROM THE NOTES OF THE LAST MEETING None |  |  |  |
| 14.EKLF.24 | UPDATES A presentation was given to the forum. - Timeline for Delivery and Action Plan:- An updated Timeline and Route Map were circulated. The developers were not present at the meeting to provide an update. - Planning Applications:- Taylor Wimpey (Parcel 19) An application for 167 dwellings and associated works was approved at a Planning Committee meeting on 17th March 2015, subject to the completion of a S106 agreement and conditions. Dwellings for this development site could not be occupied until Access E was completed. Infill Link Road – Ket/2015/0028 The provision of an infill link road approximately 750 metres in length which would provide access to the approved Primary School comprising of: - A primary street (Tree lined) - Footpath and Cycleway - A 125 metre reinforced maintenance access track (to serve the approved attenuation pond) - A Wildlife Management Area – (for translocation of the Great Crested Newt) - Four secondary access points for development parcel R22 - Drainage infrastructure - Landscaping The application was approved by the Planning Committee on 17th March 2015, subject to a number of conditions. Taylor Wimpey had also submitted a Variation of Conditions application. The application sought to vary Condition 18 and 19 of the outline planning permission for Parcel R19 only. There were no further updates but due to be determined by the Planning Committee in the summer. Persimmon (Parcels 23 & 26) A 14 day re-consultation period on the amended plans and additional information submitted, was due to finish on 7th April 2015. A Planning Committee was due to be held on 16th April, 2015 to determine the application. The amended plans included: - a layout for 332 dwellings (previously 308). - a more linear layout (in line with Design Code requirements) - removal of swale and attenuation area due to drainage into wider East Kettering development - more distinctive entrance and focal spaces - re-designed dwellings to create ‘garden suburb’ character - 20% affordable housing Hallam, David Wilson & Barratt Site (Parcels R7, R9 & R10) These parcels related to the development at the top of Deeble Road and Warkton Lane. A decision was issued on 8th January 2015. A Section 106 agreement had been signed and dated and was similar to the Alledge Brook legal agreement. The Section 278 highway works for Access D were complete and works were due to start in April 2015. A number of pre-commencement conditions were required to be discharged prior to works starting on site. - Infrastructure Primary School The name of the school had been announced as: “Hayfield Cross Church of England Primary School” and was due to open on 1st September 2015. Construction of the school was well underway and on target. A Ministerial visit by Brandon Lewis MP took place on 12th March 2015. Highway Programme - Infill link road (approved on 17th March) was expected to start in May 2015. - Access D Roundabout - groundworks were expected to start in April 2015. - Access E Double traffic light signals - Works were due to start Summer 2015 - Access F Roundabout – Likely to commence Summer 2015. Richard Hall (NCC Highways) advised the forum that issues had been raised by members of the Planning Committee with regards to the crossing of the Infill Road to the Linear Park. The developer had been asked to investigate additional use of zebra crossings in addition to the raised level tables. The A14 widening project was due to be completed by early May. Works in Barton Road could not start until the A14 widening was finished. Signalising studies were due to take place at Wicksteed Park/Windmill Ave junction when Barton Road was in a neutral position, so accurate figures could be recorded. The study would also include the Pytchley Road roundabout junction. The studies would not take place during school holidays. The Deeble Road/Windmill Avenue junction works had been targeted to start July 2015. The Woodlands Avenue junction formed part of the Redrow development in Barton Seagrave. A copy of the technical study was to be submitted. - Major Infrastructure Strategic Drainage Anglian Water Authority representatives had sent their apologies for the meeting, however, the following information had been supplied:- ‘A decision relating to the funding commitments of the Anglian Water Authority would be made by their board on 5th May 2015 and if approved would enable works to start October/November 2015.’ A timetable would be drawn up and brought to a future meeting. 1. Attenuation ponds in the centre of the site 2. Sewerage System 3. Pumping Station The technical details were to be discussed between developers and landowners. The pipeline was to go under the A14 and down to Burton Latimer round the A6. The technical information which worked out the capacity and flow rates would be available at a later date. Jct 10a A14 Business Case Funding was yet to be agreed in detail. Work was on-going to fix the works programme timetable. WeWa link road There had been a delay in bringing forward the business case but meetings were to start very soon. Health Meetings had been set for June and September where further details would be given on services to be brought to the development. | Members of the forum were encouraged to submit any objections by this date. |  |  |
| 14.EKLF.25 | QUESTIONS ON UPDATES Q Would the signalising studies at the Windmill Avenue/Barton Road junction take into account the Wicksteed Park traffic? Q Has the traffic model accounted for a 5-10% increase in current traffic flows? Q In relation to the WeWa, would the area of land around Greenpatch become a rat run? Q What code design was being worked to in relation to the dwellings? Q Was there an update on the traffic calming in Cranford? Q Are the plans fit for purpose in relation to size of garages and driveways? | A Yes, part of the work would include accessibility to and from the park. This would be considered in future proposals for design. A The traffic model was some years old, however, the one used incorporated a higher level of traffic movements. Traffic counts were to be taken of most of the junctions. A The WeWa road is to be delivered by the time 2700 dwellings are built. The technical details for the road will take into account the flow rates. A Code 4 design was being requested for Taylor Wimpey and Persimmon sites. However, Taylor Wimpey was compiling an appraisal for Code 3 design for KBC to consider. A Two proposals for Cranford and Cranford Road had been received which had been considered by Cranford Parish Council. One had been chosen which would improve the High Street and the whole of Cranford Road. Cranford Road was a priority for funding for traffic calming, there could be options for forward funding but this would only be considered if repayment was guaranteed within a year. Discussions were taking place with the developer to start landscaping in the near future. A All applications will have standard condition that garages and drives have the correct measurements to accommodate cars and parking, as detailed in the design code. |  |  |
| 14.EKLF.26 | PUBLIC QUESTION AND ANSWER SESSION Q When will a piece of Warkton Lane be ‘stocked’ up? OTHER COMMENTS NOTED It was noted by all attendees that for a second meeting the developers had not been in attendance and that this was a requirement of the forum. Anglian Water Authority representatives had attended the Planning Committee on 17th March 2015 to answer any questions in relation to the applications heard. Kettering Borough Council were responsible for the East Kettering website and the East Kettering leaflets were available from this site. Cllr Russell Roberts declared an interest as a resident of Barton Seagrave and governor of the new Primary School (PS4). | A Part of Warkton Lane is to be stocked and will form part of the works for the WeWa and would like to see it as a non-motorised lane/bridleway. Comment to be taken back to developers. | Adrian Arnold |  |
| 14.EKLF.27 | ITEMS FOR NEXT MEETING No items were submitted. |  |  |  |
| 14.EKLF.28 | DATE OF NEXT MEETING 18th June 2015 |  |  |  |

(The meeting started at 6.00 pm and ended at 7.10 pm)

Signed …………………………………………………………………………………………………

Chair

rap