Version 15

Please note that this timeline is part of on-going work and is subject to change

March 2013

April 2013

May 2013

June 2013

July 2013

August 2013

September 2013

October 2013

November 2013

December 2013

Extension of Time applications submitted (on hold until autumn)

S106 renegotiated

Full application – Taylor Wimpey

A14 jnct10a design work starting. WeWa business case being formulated

Government, HCA, LEPS, NIP Funding agreed £17.34m

Submission of Reserved Matters for Surface Water Drainage and Accesses D, E and F

Discharge and variation of conditions submitted including foul drainage.

Outline approval kept alive - RM’s submitted (Hallam & Persimmon)

RM consultations underway.

Access D being examined.

Drainage strategy being examined in detail for foul sewage

Drainage Strategy Applications submitted – Committee Approved

A14 jnct 10a and WeWa design principles and costs – on going

January 2014

February 2014

March 2014

April 2014

May 2014

June 2014

Site clearance work due to start - summer

Access D approved at committee on 27th February

Access E approved at committee on 27th February

Access F Approved at committee on 4th February

Discussions to start on District Centre design

Discharge of RMA conditions (materials etc)

Collaboration Agreement due for completion – summer.

Not Yet Completed

WeWa business case to be confirmed. A14 j10a principal costs and design agreed for funding bid.

Application for primary school submitted (PS4)

Reserved Matters - Surface Water Drainage approved by committee on 4th February

Reserved Matters - David Wilson/Barrett approved by committee on 4th February

July 2014

SUDS works due to start summer

Primary school approved by committee 23rd July

August 2014

September 2014

November 2014

December 2014

October 2014

Taylor Wimpey revised Reserved Matters application received

First Primary School (PS4) starts on site – autumn (Nov)

Foul Drainage Strategy work start.  Complete late summer 2016

Reserved Matters applications for internal road links to be submitted

Collaboration agreements due to be completed in Autumn (Nov/Dec)

Discharge of conditions for internal roads

SUDS Attenuation Basin due  winter 2014/15

Business Case for Jnct 10a to be submitted to Central Government – autumn

Taylor Wimpey & Persimmon revised Reserved Matters due to be submitted

0

January 2015

February 2015

March 2015

April 2015

May 2015

June 2015

July 2015

August 2015

September 2015

November 2015

October 2015

Access E (Barton Rd/Warkton Ln) traffic lights due to start summer

Health options discussions for District Centre on going

Taylor Wimpey possible start on site – early summer

Primary school due to open

J10 works with Roxhill development A6 alignment works due to start late summer

Potential detail RMA for District Centre - summer

Persimmon Homes possible start on site - summer

Strategic drainage due to start

Woodlands Ave due to start

Completion of Access F into site from A14 junction 10 – Autumn/Winter 2015

First house foundation due to start (David Wilson)

Taylor Wimpey Reserved Matters application due to committee

Work due to start for Access D (Warkton Ln/Deeble Rd), other road improvements and traffic calming works – spring

Access F works due to start Phase 1 interim – summer 2015

Persimmon due to committee April/June

January 2016

February 2016

March 2016

April 2016

May 2016

June 2015

July 2016

August 2016

September 2016

December 2016

November 2016

October 2016

Other RMA for housing parcels to be submitted

By end of 2016 another 190 houses due to be available

SUDS Drainage due for completion

Roxhill Business Park reserved matters application potentially due in

Layout of Public Open Space due in

Possible timetable for Jct 10a delivery could be set out summer 2016. Possible start on site 2021/2022

Work on the district Centre reserved matter applications

We Wa link road technical work ongoing

Road from Access E (Barton Rd/ Warkton Ln) to the school due to be completed

Possible 200 – 220 houses started

Potentially 15 houses complete.

December 2015

Technical work on J10a may start

First house completed Autumn/Winter

Layout of Public Open Space due in