- INFORMATION

2.1	At the Planning Policy Committee meeting of the 25th November 2004 the Committee endorsed the Draft Local Development Scheme. A revised scheme for Kettering Borough was subsequently agreed at the Planning Policy Committee of 26th January 2005 with the recommendation that the Executive agree the revised Local Development Scheme.

2.2	The Scheme considered at the meeting of 25th November 2004 included a draft Schedule of proposed Local Development Documents and profiles indicating plan type, title and key milestones. The Joint Planning Unit has now received advice from the Government Office for the East Midlands indicating the need to achieve a high confidence of delivery of any Development Plan Document listed in the Scheme and suggesting an initial minimal approach when assessing requirements. In addition the Planning Support Grant will relate to the achievement of milestones within the Scheme.

2.3	It is therefore proposed that the plans and timescales within the scheme, in so far as it relates to Kettering Borough, be amended as indicated in Appendix 1. A copy of the full Scheme is available in the Members Room. In relation to Kettering Borough Council It is proposed that the following development Plan Documents be delayed: -

- Desborough Town Centre Area Action Plan

- Ise Valley Area Action Plan

- Burton Latimer Town Centre Area Action Plan

- Burton Latimer Urban Extension Area Action Plan.

and be deleted from the scheme.

The timescales for the delivery of the other plans, with the exception of the Kettering Urban Extension Area Action Plan, have been delayed.

2.4	With regard to those plans which have been deleted work is proposed to progress on the Desborough and Burton Latimer town centre plans outside the Local Development Framework (LDF) process for the interim period. The Burton Latimer Urban Extension Area Action Plan is proposed to be delivered at a later stage and the Ise Valley Area Action Plan is proposed to be incorporated within the Site Specific Local Development Document (LDD). The Rothwell and Desborough Area Action Plans have been combined. The Scheme will be subject to review against progress and plans can be included at a later date. Supplementary Planning Guidance specific to Kettering Borough is now identified within the scheme to be saved.

2.5	As the Joint Committee is not in place to approve the Local Development Scheme, which needs to be submitted to the government Office by 31st March 2005, it is therefore now necessary for this Council to agree the Scheme for Kettering as opposed to endorse the scheme subject to approval by the Joint Committee. The Scheme will then be progressed as a compendium of documents and forwarded to the Government Office through the Joint Planning Unit. In terms of joint planning documents the only Supplementary Planning Guidance (SPG) now identified relates to developer contributions.

3.	CONSULTATION AND CUSTOMER IMPACT

The Local development Scheme will continue to be progressed by the Joint Planning Unit.

4.	POLICY IMPLICATIONS

The draft Local Development Scheme has a key part in coordinating planning activity across North Northamptonshire. It will determine the work programme and resource needs of the Joint Planning Unit and planning policy teams of the Councils.

5.	FINANCIAL/RESOURCE IMPLICATIONS

None.

Background Papers:

Title of Document: Draft Local Development Scheme

Date:

Contact Officer: Kathleen Rivett

# Text boxes

1.	PURPOSE OF REPORT

To inform the Executive of the Planning Policy Committee’s agreement to proposed changes to the Draft Local Development Scheme and seek approval of the scheme for progression to full Council.

6.	RECOMMENDATION

The Policy and Enabling Manager (Planning) recommends that the Executive agree the Local Development Scheme and that it be forwarded to full Council for  approval.