Figure 2: North Northamptonshire Joint Local Development Framework - the suite of Local Development Documents (LDDs)

Joint Spatial Strategy LDD

Development Control LDD

| Corby Proposals map | Kettering Proposals map | East Northants Proposals map | Wellingborough Proposals map |
| --- | --- | --- | --- |

| Site specific policies LDD | Site specific policies LDD | Site specific policies LDD | Site specific policies LDD |
| --- | --- | --- | --- |

| Kingswood + Lincoln Area Action Plan (AAP) | Corby urban extension AAP | Corby town centre AAP | Rothwell & Desborough urban extension AAP | Kettering town centre AAP | Kettering urban extension AAP | Higham Ferrers, Irthlingboro’+ Rushden AAP | Raunds AAP | Thrapson + Oundle AAP | Well’boro’ town centre AAP | Well’boro urban extension/s AAP/s |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Developer contributions- strategy and guidance Supplementary Planning Document (SPD) | Conservation strategy SPD | Shopfront design + security SPD | Land East of Eastfield Road Development Brief SPD | Park Farm Way/ Shelley Rd Devt Brief SPD | Public Art – Guide to good practice SPD | Land at High Street,Development Brief SPD |
| --- | --- | --- | --- | --- | --- | --- |

|  | LDDs prepared and agreed jointly |
| --- | --- |
|  | LDDs/SPDs prepared jointly but where necessary agreed by individual councils |
|  | LDDs/SPDs prepared by Corby Borough Council |
|  | LDDs/SPDs prepared by Kettering Borough Council |
|  | LDDs/SPDs prepared by East Northamptonshire Borough Council |
|  | LDDs/SPDs prepared by the Borough Council of Wellingborough |

| Document title | Status | Responsible authority | Brief description | Chain of conformity | Early stakeholder + community involvement | Consultation on preferred options and proposals | Date for submission to SofS | Proposed date for adoption |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kettering BC Site-Specific Proposals LDD | DPD | KBC | Policy framework containing land allocations and site-specific proposals in Kettering District. | To conform with the Spatial Strategy LDD. |  | March 2006 | Sept 2006 | Sept 2007 |
| Kettering BC Proposals map LDD | DPD | KBC | Illustration of policies and proposals on ordnance survey base. | To conform with the Spatial Strategy, Development Control, Site Specific Proposals and AAP LDDs. | N/A | May 2005 | November 2005 | December 2006 |
| Rothwell & Desborough Urban Extension Area Action Plan | DPD | KBC | Address the planned expansion of Rothwell, & Desborough setting out detailed requirements of new development. | To conform with the Spatial Strategy and Site-Specific Proposals LDDs |  | May 2005 | November 2005 | December 2006 |
| Kettering Town Centre Area Action Plan | DPD | KBC | Provide a framework to co-ordinate the enhancement of Kettering town centre. | To conform with the Spatial Strategy and Site-Specific Proposals LDDs |  | January 2006 | June 2006 | June 2007 |
| Kettering Urban Extension/s Area Action Plan/s | DPD | KBC | Address the planned expansion of Kettering, setting out detailed requirements of new development. | To conform with the Spatial Strategy and Site-Specific Proposals LDDs |  | September 2005 | March 2006 | March 2007 |

Title: Kettering Borough Site Specific Proposals

| Document details | Role and subject This LDD will set out policies for proposals that relate to specific parts of Kettering Borough, including both land allocations and site specific development control policies. The exception will be key areas of change, identified on the Proposals Map, to be subject to Area Action Plans. The LDD will include the identification of sites for housing, employment, recreation and other land uses and will contain policies relating to specific areas where individual development, conservation or design considerations apply, e.g. specific design or density policies; Important Open Land designations; Conservation Areas; Geographical coverage The administrative District of Kettering Borough Status Development Plan Document Chain of conformity PPS RSS North Northamptonshire Core Strategy, Proposals Map and Development Control Policies LDD |
| --- | --- |
| Timetable | Completion of pre-production /survey phase (initial - linked to core policies/d.c. policies DPDs Start of consultation on preferred options report Submission of DPD to SofS Public consultation period on submission DPD Examination period, including target date for examinations Receipt of Inspectors binding report Adoption and publication | September 2005 March 2006 September 2006 To December 2006 To March 2007 June 2007 September 2007 |
| Arrangements for production | Organisation leading the process Kettering Borough Council Management arrangements The LDD will be agreed by the Kettering Borough Council following consideration by the KBC Executive and Overview and Scrutiny Committees. Its preparation, including drafting and consultation, will be managed by the KBC Planning Policy Committee. Resources required to produce the LDD Policy & Implementation Section Approach to involving stakeholders and the community Refer to SCI |

| Title: Kettering Borough Proposals Map |
| --- |
| Document details | Role and subject The proposals map will illustrate on an Ordnance Survey base map all the policies and proposals contained in development plan documents and saved policies. It will reflect the Key Diagram in the Joint Spatial Strategy, and it will contain Insets showing the proposals within specific areas (e.g. sites subject to development allocation; Area Action Plans; or sites to which policies apply for protection and/or enhancement). Geographical coverage The map will cover the administrative district of Kettering Borough. Status Development Plan Document Chain of conformity PPS RSS North Northamptonshire Core Strategy and Development Control Policies LDD |
| Timetable | Completion of pre-production /survey phase (initial - linked to core policies/d.c. policies DPDs Start of consultation on preferred options report Submission of DPD to SofS Public consultation period on submission DPD Examination period, including target date for examinations Receipt of Inspectors binding report Adoption and publication | Ongoing May 2005 November 2005 On going On going On going On going |
| Arrangements for production | Organisation leading the process Kettering Borough Council Management arrangements The LDD will be agreed by the Kettering Borough Council following consideration by the KBC Executive and Overview and Scrutiny Committees. Its preparation, including drafting and consultation, will be managed by the KBC Planning Policy Committee. Resources required to produce the LDD Policy & Implementation Section Plus external resources to be procured from company providing cartographic, printing and online information Approach to involving stakeholders and the community Refer to SCI |

| Title: Rothwell & Desborough Urban Extension Area Action Plan |
| --- |
| Document details | Role and subject This LDD will set out the vision and detailed policies for the Rothwell & Desborough urban extension. The LDD will include the identification of sites for housing, employment, recreation and other land uses within the urban extension. Geographical coverage Rothwell & Desborough urban extension Status Development Plan Document Chain of conformity PPS RSS North Northamptonshire Core Strategy, Proposals Map and Development Control Policies LDD |
| Timetable | Completion of pre-production/survey phase Start of consultation on preferred options report Submission of DPD to SofS Public consultation period on submission DPD and alternative sites Examination period, including target date for examinations Receipt of Inspector’s binding report Adoption and publication. | Underway May 2005 November 2005 To January 2006 To June 2006 October 2006 December 2006 |
| Arrangements for production | Organisation leading the process Kettering Borough Council Management arrangements The LDD will be agreed by the Kettering Borough Council following consideration by the KBC Executive and Overview and Scrutiny Committees. Its preparation, including drafting and consultation, will be managed by the KBC Planning Policy Committee. Resources required to produce the LDD Policy & Implementation Section Approach to involving stakeholders and the community Refer to SCI. |

| Title: Kettering Town Centre Area Action Plan |
| --- |
| Document details | Role and subject This LDD will set out policies and proposals for Kettering Town Centre. The aim of the LDD will be to enhance the vitality and viability of the town centre bye considering issues of growth, distribution of land uses, access, and improvements to the public realm. It will take into account the town centre masterplan and other research projects relating to Kettering and the neighbouring town centres in North Northamptonshire. Geographical coverage Kettering Town Centre Status Development Plan Document Chain of conformity PPS RSS North Northamptonshire Core Strategy, Proposals Map. |
| Timetable | Completion of pre-production/survey phase (inc. Town Centre Masterplan) Start of consultation on preferred options report (in parallel with Core Strategy) Submission of DPD to SofS Public consultation period on submission DPD and consult on alternatives Examination period, including target date for examinations Receipt of Inspector’s binding report Adoption and publication. | Underway January 2006 June 2006 To August 2006 To January 2006 April 2007 June 2007 |
| Arrangements for production | Organisation leading the process Kettering Borough Council Management arrangements The LDD will be agreed by the Kettering Borough Council following consideration by the KBC Executive and Overview and Scrutiny Committees. Its preparation, including drafting and consultation, will be managed by the KBC Planning Policy Committee. Resources required to produce the LDD Policy & Implementation section Approach to involving stakeholders and the community Refer to SCI |
| Title: Kettering Urban Extension/s Area Action Plan/s |
| Document details | Role and subject This LDD will set out the vision and detailed policies that relate to the Kettering Urban Extension. The LDD will set out details of land uses and infrastructure as well as area specific planning policies. Geographical coverage Kettering Urban Extension Area Status Development Plan Document Chain of conformity PPS RSS North Northamptonshire Core Strategy, Proposals Map and Development Control Policies LDD. |
| Timetable | Completion of pre-production/survey phase Start of consultation on preferred options report Submission of DPD to SofS Public consultation period on submission DPD and consult on alternatives Examination period, including target date for examinations Receipt of Inspector’s binding report Adoption and publication. | To August 2005 September 2005 March 2006 To May 2006 To November 2006 January 2007 March 2007 |
| Arrangements for production | Organisation leading the process Kettering Borough Council Management arrangements The LDD will be agreed by the Kettering Borough Council following consideration by the KBC Executive and Overview and Scrutiny Committees. Its preparation, including drafting and consultation, will be managed by the KBC Planning Policy Committee. Resources required to produce the LDD Policy & Implementation section Approach to involving stakeholders and the community Refer to SCI |

# Text boxes

Joint Local Development Scheme

Joint Statement of Community Involvement