Alcohol Harm Reduction Action Plan v.8

| OUTCOMES | ACTIVITY | Actions | MEASURES | TARGET Y1 Y2 Y3 |  |  | OWNER | RESOURCES | LINKS TO OTHER PLANS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Increased awareness of alcohol effects and consequences among target groups (young people and middle aged drinkers) | Deliver an Alcohol Social Marketing Campaign | - Identify target groups (Young People & Middle-aged drinkers) - Consult with stakeholders - Identify key messages - Develop resource materials/interventions - Launch materials/interventions - Campaigns targeting middle-aged drinkers & young people in schools and universities. | increase awareness of alcohol effects and consequences among target groups (metrics to be defined e.g. number of increased referrals to alcohol treatment services Can & Aquarius Tier 2 & 3) Contribute to halting the rate of increase in alcohol related hospital admissions |  |  |  | Pam Berry/ Comms NHSN | £270k |  |
| Everyone has access to appropriate information | Deliver an alcohol communications strategy | - Write and deliver a communications strategy - Review membership and Terms of reference of Better education Better Communication group to lead this work - Identify the resources to support alcohol communications work with contributions from a range of agencies - Create and maintain an alcohol services directory. - Provide information to parents on accepted good practice for managing alcohol in the home with children & young people |  |  |  |  | - Lead communication representative from each organisation - Terry Pearson DAAT/NHSN/CYPB - CYPPB |  | CYPP |
|  | Provide alcohol training to all frontline staff across partner organisations | - DAAT to continue to commissions this training programme on behalf of NHSN. - Current training programme to be evaluated and recommendations to be implemented across the county. - To implement a monitoring system by agency to identify the number of individuals referred. - Employers encouraged to adopt alcohol policies and practises that reduce alcohol harm |  |  |  |  | Terry Pearson/DAAT NHSN Dawn Wintle & Lorraine Pollard | 13K |  |
| Reduction in accessibility to cheap alcohol in Northamptonshire (for vulnerable groups) | Explore effect of minimum pricing | - Support for and evaluation of Kettering pilot and implementation of recommendations across Northants - Declaration of Health and Well Being to include minimum price if appropriate | Inclusion of commitment to reduce access to cheap alcohol across the county as part of proposed Declaration |  |  |  | ACG FG (NHSN) |  |  |
| A safe and vibrant night-time economy (especially in Northampton and Kettering?) | Promotion and Expansion of Best Bar None | - Multi-agency support to deliver BBN thereby improving standards in the On-trade accompanied by publicity and education of public as to what BBN means to them thereby increasing public confidence | NI 17: Perceptions of anti-social behaviour |  |  |  | Andy Tresias Mark Worthington |  |  |
|  | Maintaining links with licensees | - Alcohol strategy principles are delivered to the trade through appropriate fora (eg Pubwatch) | NI 20: Assault with injury crime rate |  |  |  | Mark Worthington Ian Fletcher |  |  |
|  | Influence planning decisions | - Planning applications |  |  |  |  | Andy Tresias |  |  |
|  | Promoting responsible selling of alcohol | - Ensure compliance with new law – statutory code - Multi-agency inspections of premises - Checking policies and procedures - Risk-assessment of drinks promotions | NI 17: Perceptions of anti-social behaviour |  |  |  | Andy Tresias |  |  |
|  | Targeting irresponsible sellers | - Collection and analysis of data to support work in dealing with alcohol and issues with specific suppliers. - Proactive enforcement campaign “No drink to drunks” & underage sales supported by review process where appropriate | NI 41: Perceptions of drunk or rowdy behaviour as a problem |  |  |  | Carol Gamble Trading Standards |  |  |
|  | Re-launch Operation Nightsafe | - Promotion of Polycarbonate glasses - Assessment of drinks promotions and challenge where inappropriate | NI 15: Serious violent crime rate |  |  |  | Mark Evans Police |  |  |
| Consistent licensing practice & review | Developing Licensing committees | - Ensure effective use of powers under the Licensing Act 2003 - Awareness raising event for licensing councillors and trade - Develop Local licensing policy for each authority area |  |  |  |  | Local Authority lead? |  |  |
|  | Licensing reviews | - Multi-agency Licensing Enforcement partnerships (LEPs) direct evidence gathering and enforcement to allow greater use of powers - Improvements to the collection and effective use of local intelligence to inform the review of the ‘Statement of Licensing Policy’ by the Licensing Authority |  |  |  |  | Andy Tresias | Core Business | National Alcohol Strategy |
|  | Strategic review of the number and location of licensed premises | - Mapping exercise to identify licensed premises - Multi-agency strategic review of the findings - LAs to consider saturation/ cumulative impact policies - Apply review to local licensing policy and work with licensing committees to implement |  |  |  |  | ACG |  |  |
| Reduction in hospital related admissions | NHSN £1.1million investment into reducing alcohol related admissions through treating patients more effectively in the community | - Increase capacity of Tier 3 community detox - Improve efficiency of Tier 4 inpatient detox. - Increasing capacity of Tier 3 structured specialist community based treatment. | - Reduction in waiting times for community based detox from 6 months to 1 month - Reduce waiting times for community based specialist treatment from 6-8 weeks to 1week - To reduce the risk of relapse and providing tier 2 support to intervene with increasing and higher risk drinkers |  |  |  | Terry Pearson DAAT/NHSN Pam Berry/Dawn Wintle | Part of £1.1 million NHSN investment |  |
|  | On-going funding of 2 Alcohol Liaison Nurses | - Signposting to community related treatments services - Provide alcohol advice and support to acute trust patients | NI 39: Alcohol-harm related hospital admission rates |  |  |  | DAAT/NHSN Pam Berry/Dawn Wintle | £70k |  |
|  | Continue (Intervention and Brief Advice) IBA training for frontline staff | - Alcohol clinics for lower level risky drinkers and referral into treatment systems for others - A volunteer programme to work with dependant drinkers and support them through treatment |  |  |  |  | This has gone from Fiona’s action plan. Should this be under outcome 2? |  |  |
| Increased number of patients who complete treatment. | Develop Alcohol care pathways for primary secondary care | - Consult with all stakeholders - Promote awareness of Care Pathways - Developing Tier 2 treatment services to provide family services, aftercare & diversionary services for increasing high risk drinkers | Number of additional community based treatment | 751 | 1501 | 1501 | Dawn Wintle NHSN/DAAT | Develop Alcohol care pathways for primary secondary care |  |
|  | Develop care pathways for patients with dual diagnosis of alcohol misuse and mental health issues | - Consult with key stakeholders - Promote awareness of care pathways |  |  |  |  | DAAT/NHSN Fiona Grant |  |  |
|  | Support Alcohol Treatment Requirement (ATR) | Treatment of dependent drinkers on probation |  |  |  |  | Probation |  |  |
|  | Support Alcohol Specified Activity Requirements (ASARs) | Treatment of higher risk drinkers on probation |  |  |  |  | Probation |  |  |
|  | Introduce Alcohol treatments in prisons | Treatment for higher risk and dependent drinkers in prisons |  |  |  |  | NHS Northants |  |  |
| Improved use and sharing of data between organisations | Develop a format for reporting Hospital Attributable Admissions (NI39) | - Establish the feasibility of conducting Emergency Department alcohol project, this includes, provision of brief advice to people attending Emergency Department and sign posting to other services, targeted information on alcohol misuse. - Improve data collection and recording of A & E alcohol attendances |  |  |  |  | NHSN (Marie McLoughlin/Lorraine Pollard Dan Beames?/June Whitney |  |  |
|  | Development of enhanced A&E data collection for alcohol related attendances | - Contract negotiations with Acute Trusts to implement proposal |  |  |  |  | NHSN (Marie McLoughlin/Lorraine Pollard) Dan Beames? |  |  |
| Earlier identification of individuals with alcohol misuse behaviours | Promote expansion of Direct Enhanced Services (DES) in Primary Care | - Liaise with GP contracting within NHSN - Develop care path for risky, higher risk and dependent drinkers for appropriate treatment | Terry |  |  |  | NHSN commissioners |  |  |
|  | Increase capacity and capability within primary care to enable identification of those drinking at increasing and higher risk levels | - Evaluation of GP primary care project to enhance existing activity. - Explore expansion of current activity to cover gaps identified by GP project | Increased treatment and referral in Primary Care |  |  |  | DAAT/NHSN/ CAN/Aquarius |  |  |
|  | Develop an Alcohol intervention programme in A&E departments for those presenting with an alcohol related injury | - Training of staff in identification screening and referral |  |  |  |  |  |  |  |
|  | Develop the alcohol Arrest referral Scheme based in custody suites | - Consider alternative referral and disposal processes |  |  |  |  | DAAT | £130k pa until Oct 2010 | HO pilot scheme |
| Reduced perception of ASB (Single Confidence measure) | Consider ways of improving criminal justice processes for offenders of alcohol related incidents |  |  |  |  |  | LCJB |  |  |
|  | Introducing Community Alcohol Partnerships | - Target young people demonstrating the initial signs of alcohol-related anti-social behaviour through a programme of positive interventions and referrals | NI 21: Dealing with local concerns about anti-social behaviour and crime by the local council and police |  |  |  |  |  |  |
|  | Recruitment of 3 alcohol outreach workers (RIEP) | - Work with Safer Community Teams and ASB units to target ASB hotspots |  |  |  |  | DAAT |  |  |
| Improve understanding of young peoples attitudes towards alcohol | Research by University of Northampton (RIEP) | - Evaluation of report and implementation of recommendations |  |  |  |  | Uni |  |  |
| Reduction of road casualties | Zero tolerance to drink driving | - Need actions |  |  |  |  | John Spencer |  |  |