## P V A 31.03.11
KBC Audit Plan 2010/11 - comparison of planned and actual work
Description of Audit activity | Status | Assurance Level
Core Financial Systems - planned work
Accounting Systems | Completed | Acceptable
Cashiers and Banking | Completed | Acceptable
CFS IT Application Controls | Draft report issued 13/04/11 - awaiting response from IT and Finance | Acceptable
Council Tax | Completed | Acceptable
Creditors | Completed | Limited
Housing Benefits | Completed | Acceptable
Housing Rents | Completed | Acceptable
National Non Domestic Rates | Completed | Acceptable
Payroll | Completed | Acceptable
Sundry Debtors | Completed | Acceptable
Treasury Management | Completed | Acceptable
Other planned work
Anti Fraud & Corruption Arrangements | Draft report issued 08/04/11 - discussion with Head of Finance 09/05/11 - awaiting agreement of implementation dates | Limited
Building Security Arrangements | In progress - delay due to sickness within the audit team
Town Centre Redevelopment | Deleted with the agreement of the Head of Finance due to greater priority additional work
Connect Law | Completed | Limited
Housing Repairs | Deleted with the agreement of the Head of Finance due to greater priority additional work | N/A
Human Resources | Deleted with the agreement of the Head of Finance due to greater priority additional work | N/A
Partnerships Review | Draft report issued 19/04/11 - Head of Corporate Development has agreed content but taking report to CMT to agree implementation | Limited
Planning & Development Control | Completed | Substantial
Procurement | Aborted - audit included in 2011/12 plan | N/A
Stores | Deleted with the agreement of the Head of Finance due to greater priority additional work | N/A
Grant Claim Verification | Completed | N/A
PI Checks | Completed | Full
Additional projects
Core Financial Systems - Fixed Assets & Capital Accounting | Completed | Substantial
Property services overtime | Draft report issued 30/03/11 - awaiting agreement of implementation dates by Head of Environmental Care Services | Limited
AGS/Fraud Survey | Completed | N/A
RTB leasehold properties | Completed | Limited