## Cap Prog - Summary
REVIEW OF THE CAPITAL PROGRAMME - AUTUMN 2004
|  | 2004/05 | [6 empty] | 2005/06 | 2006/07
|  | Original Estimate | Carry Fwds | Cttee Changes | CAMT Changes | Adj Estimate | Prop Ctte Changes | Latest Estimate | Indicative Estimate | Indicative Estimate
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
1. EXPENDITURE SUMMARY:
| A. HOUSING SCHEMES (HRA) | 3189 | 108 | 0 | 0 | 3297 | -878 | 2419 | 2971 | 2971
B. GENERAL FUND SCHEMES:
| Private Sector Housing Improvement | 625 | 175 | 0 | 0 | 800 | 0 | 800 | 675 | 675
| Investment & Repair Programme | 431 | 291 | 33 | 0 | 755 | -50 | 705 | 580 | 80
| Community Project Schemes | 1331 | 312 | 45 | -118 | 1570 | 10 | 1580 | 2092 | 1611
| E-government investment programme | 1034 | 467 | 175 | 0 | 1676 | 262 | 1938 | 466 | 0
| Invest To Save Projects | 0 | 30 | 0 | 30 | 60 | 0 | 60 | 200 | 200
| Total | 6610 | 1383 | 253 | -88 | 8158 | -656 | 7502 | 6984 | 5537
2. FINANCING ANALYSIS:
| Major Repairs Allowance | 2807 | [5 empty] | 2419 | 2971 | 2971
| Contribution from HRA | 470 | [5 empty] | 395 | 395 | 395
| Capital Receipts | 3771 | [5 empty] | 2538 | 957 | 900
| Transitional Capital Receipts | 0 | [5 empty] | 710 | 675 | 675
| External Borrowing | 0 | [5 empty] | 0 | 1137 | 121
| E-Government Grant | 0 | [5 empty] | 482 | 150 | 0
| Defra Recycling Grant | 416 | [5 empty] | 725 | 464 | 0
| Other Contributions | 186 | [5 empty] | 233 | 235 | 475
| Total | 7650 | [5 empty] | 7502 | 6984 | 5537
3. CAPITAL RECEIPTS FORECAST:
| B/fwd | 1664 | [5 empty] | 1895 | 57 | 0
| Consumption In Year | -3771 | [5 empty] | -2538 | -957 | -900
| Addition In Year | 2127 | [5 empty] | 700 | 900 | 900
| C/fwd | 20 | [5 empty] | 57 | 0 | 0
4. TRANS ARRANGEMENTS RECEIPTS
| B/fwd | [6 empty] | 0 | 590 | 781
| Consumption In Year | [6 empty] | -710 | -675 | -675
| Addition In Year | [6 empty] | 1300 | 866 | 433
| C/fwd | [6 empty] | 590 | 781 | 539
Note on J29: Gsoulsby: Of the original grant of £400, only £268 was spent by end of 03/04 - therefore £132 carried fwd in addition to the £350 awarded in the year.
APPENDIX 1

## Cap Prog - Detail
REVIEW OF THE CAPITAL PROGRAMME - AUTUMN 2004
| 2004/05 | [5 empty] | 2004/05 | 2005/06 | 2006/07 |  |  | Corporate Priority Matching | [9 empty] | Asset Mgt
Scheme | Original Estimate | Carry Fwds | Cttee Changes | CAMT Changes | Adj Estimate | Prop Ctte Changes | Latest Estimate | Indicative Estimate | Indicative Estimate |  | Scheme(s) Committed | 1A | 1B | 1C | 2A | 2B | 3A | 4A | 5A | 6A | 6B
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 |  | Yes / No
HOUSING REVENUE ACCOUNT
Kitchen & Bathroom Renewal | [15 empty] | ü | [5 empty] | ü
Contract 7 - Pipers Hill Estate | 5 |  |  |  | 5 |  | 5 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 8 - Weekley Glebe Estate - Ph 1 | 11 |  |  |  | 11 |  | 11 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 8 - Weekley Glebe Estate - Ph 2 | 40 |  |  |  | 40 | 53 | 93 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 9 - Grange Estate - Phase 1 | 8 | 92 |  |  | 100 | -32 | 68 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 9 - Grange Estate - Phase 2 | 298 |  |  |  | 298 | -200 | 98 |  |  |  | No |  |  |  |  | ü | [5 empty] | ü
Contract 9 - Grange Estate - Phases 3 & 4 | 626 |  |  |  | 626 | -419 | 207 |  |  |  | No |  |  |  |  | ü | [5 empty] | ü
Contract 10 - Pytchley Road Estate | 339 |  |  |  | 339 | -227 | 112 |  |  |  | No |  |  |  |  | ü | [5 empty] | ü
Contract 11 - Burton Latimer - Phase 1 & 2 | 459 | 16 |  |  | 475 |  | 475 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Sheltered Accommodation Upgrading | [15 empty] | ü | [5 empty] | ü
Hazeland House, Desborough | 10 |  |  |  | 10 |  | 10 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Stair Lifts - Common Areas | 100 |  |  |  | 100 | -100 | 0 |  |  |  | No |  |  |  |  | ü | [5 empty] | ü
Window Renewal Programme | [15 empty] | ü | [5 empty] | ü
Contract 11 - Miscellaneous dwellings | 6 |  |  |  | 6 |  | 6 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Naseby Rd Est - Phase 1 | 275 |  |  |  | 275 |  | 275 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
21 London Road Kettering | 20 |  |  |  | 20 |  | 20 |  |  |  | No |  |  |  |  | ü | [5 empty] | ü
Central Heating | [15 empty] | ü | [5 empty] | ü
Contract 8 - Weekley Glebe | 8 |  |  |  | 8 |  | 8 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 10 - Pytchley Road Estate | 5 |  |  |  | 5 |  | 5 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 11 - Burton Latimer/Villages - Ph 1 | 5 |  |  |  | 5 |  | 5 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 11 - Burton Latimer/Villages - Ph 2 | 102 |  |  |  | 102 | 136 | 238 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 12 - Barton Seagrave | 10 |  |  |  | 10 |  | 10 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 13 - Burton Latimer | 7 |  |  |  | 7 |  | 7 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 14 - Villages - Phase 1 | 343 |  |  |  | 343 |  | 343 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 14 - Villages - Phase 2 | 196 |  |  |  | 196 |  | 196 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Contract 15 - Miscellaneous Dwellings | 132 |  |  |  | 132 |  | 132 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Ad-hoc central heating installations | 75 |  |  |  | 75 |  | 75 |  |  |  | Yes |  |  |  |  | ü | [5 empty] | ü
Environmental Improvements | 89 | 0 |  |  | 89 | -89 | 0 |  |  |  | No |  |  |  |  | ü
Disabled Facilities Works | 20 | 0 |  |  | 20 |  | 20 |  |  |  | Yes |  |  |  |  | ü |  |  | ü
Sub Total | 3189 | 108 | 0 | 0 | 3297 | -878 | 2419 | 2971 | 2971
GENERAL FUND
Private Sector Housing Improvement
Rolling Programme:
Renovation Grants | 425 | 0 |  |  | 425 |  | 425 | 425 | 425 | As per Niall. | Yes |  |  |  |  | ü
Social Housing Grants | 200 | 175 |  |  | 375 |  | 375 | 250 | 250 |  | Yes |  |  |  |  | ü
Sub Total | 625 | 175 | 0 | 0 | 800 | 0 | 800 | 675 | 675
Investment & Repair Programme
Repair/Replacement:
Burton Latimer Offices - Windows | 0 | 18 |  |  | 18 |  | 18 | 0 | 0 | As per R.Waterfield to roll into 04/05. | No | [10 empty] | ü
Faraday Fountain | 0 | 11 |  |  | 11 |  | 11 | 0 | 0 | Have left the original budget in as lottery funding to cover the rest - Clive Millar sorting. | Yes |  |  |  |  | ü | [5 empty] | ü
Various - Lighting, Fence, Hedge & Signage | 0 | 10 |  |  | 10 |  | 10 | 0 | 0 |  | Yes | [10 empty] | ü
Pastures C'van Site - Surfacing/Fencing | 132 |  |  |  | 132 |  | 132 | 0 | 0 |  | Yes |  | ü | [8 empty] | ü
Crematorium Grounds - Various works | 28 |  |  |  | 28 |  | 28 | 94 | 26 |  | Yes | [10 empty] | ü
Kettering Town Centre - CCTV | 28 |  |  |  | 28 |  | 28 | 22 | 0 |  | Yes |  | ü | [8 empty] | ü
Well Lane - Railings | 9 |  |  |  | 9 |  | 9 | 0 | 0 |  | Yes | [10 empty] | ü
Depot - Various Works | 0 |  | 22 |  | 22 |  | 22 | 98 | 0 |  | Yes | [10 empty] | ü
Mansfield Close Car park - Resurfacing | 0 |  |  |  | 0 |  | 0 | 69 | 0 |  | No |  |  |  |  | ü | [5 empty] | ü
Burghley Close - Resurfacing | 0 |  |  |  | 0 |  | 0 | 56 | 0 |  | No |  |  |  |  | ü | [5 empty] | ü
Car Parks - Pay & Display Machines | 0 |  |  |  | 0 |  | 0 | 44 | 0 |  | No | [7 empty] | ü | ü |  | ü
Rothwell Parish Church - Railings | 0 |  | 11 |  | 11 |  | 11 | 0 | 0 |  | Yes | [10 empty] | ü
Enhancements:
CCTV Matrix | 33 |  |  |  | 33 |  | 33 | 0 | 0 |  | Yes |  | ü | [8 empty] | ü
Improvements:
KCLL - Building Improvements | 47 | 24 |  |  | 71 |  | 71 | 47 | 54 |  | Yes |  |  | ü | [7 empty] | ü
Desborough Cemetery - Landscaping | 0 | 20 |  |  | 20 |  | 20 | 0 | 0 |  | Yes | [10 empty] | ü
Art Gallery & Museum - CCTV | 0 | 10 |  |  | 10 |  | 10 | 0 | 0 |  | Yes |  |  | ü | [7 empty] | ü
Art Gallery Lighting | 0 | 1 |  |  | 1 |  | 1 | 0 | 0 |  | Yes |  |  | ü | [7 empty] | ü
DDA Works | 0 | 170 |  |  | 170 |  | 170 | 20 | 0 |  | Yes | [7 empty] | ü |  |  | ü
East Brook Culvert Survey | 0 | 18 |  |  | 18 |  | 18 | 0 | 0 |  | Yes | [10 empty] | ü
KLV Lake | 0 | 9 |  |  | 9 |  | 9 | 0 | 0 |  | Yes | [10 empty] | ü
Art Gallery - Storage Improvements | 6 |  |  |  | 6 |  | 6 | 0 | 0 |  | Yes | [10 empty] | ü
Municipal Offices - Various upgrades | 148 |  |  |  | 148 | -50 | 98 | 130 | 0 |  | Yes | [10 empty] | ü
Sub Total | 431 | 291 | 33 | 0 | 755 | -50 | 705 | 580 | 80
Community Project Schemes
Rolling Programme:
Various Parks - Cycle Access | 0 |  |  |  | 0 |  | 0 | 93 | 109 |  | No |  |  |  |  | ü
Repair/Replacement:
Ise Pavilion Enclosure | 0 | 15 |  |  | 15 |  | 15 | 0 | 0 |  | Yes |  | ü | [8 empty] | ü
Dunkirk Ave Rec - Replace Fencing | 23 |  |  |  | 23 |  | 23 | 0 | 0 |  | Yes |  | ü | [8 empty] | ü
KLV - Synthetic Pitch Replacement | 0 |  |  |  | 0 |  | 0 | 183 | 0 |  | No | [10 empty] | ü
One Stop Shop - Accomodation | 0 |  |  |  | 0 |  | 0 | 111 | 0 |  | No | [7 empty] | ü |  |  | ü
Ise Multiplay - Resurfacing | 0 |  |  |  | 0 |  | 0 | 50 | 0 |  | No | [10 empty] | ü
King George V Fence - Replace | 0 |  |  |  | 0 |  | 0 | 18 | 0 |  | No | [10 empty] | ü
Church Walk Railings - Replacement | 0 |  |  |  | 0 |  | 0 | 14 | 0 |  | No | [10 empty] | ü
Enhancements:
Borough Wide - Recycling Project | 831 | 77 |  |  | 908 |  | 908 | 691 | 694 |  | Yes |  |  |  | ü
Grays Field - Youth Equipment | 0 | 20 |  |  | 20 |  | 20 | 0 | 0 |  | No |  | ü
Digital Recording of CCTV | 0 | 25 |  |  | 25 |  | 25 | 0 | 0 |  | Yes |  | ü
Green Patch - Agricultural Equipment | 91 |  |  |  | 91 |  | 91 | 0 | 0 |  | Yes |  |  | ü
Various Play Areas - Young Things Things | 64 |  |  |  | 64 |  | 64 | 177 | 53 |  | Yes |  |  | ü
Desborough - Young Things Things | 34 |  |  |  | 34 |  | 34 | 0 | 0 |  | Yes |  |  | ü
Play Equipment- Slade Valley | 0 | 3 |  |  | 3 |  | 3 | 0 | 0 |  | Yes |  |  | ü
Play Equipment - Well Lane | 0 | 6 |  |  | 6 |  | 6 | 0 | 0 |  | Yes |  |  | ü
Desborough - Play Equipment | 34 |  |  |  | 34 |  | 34 | 0 | 0 |  | Yes |  |  | ü
Village Halls | 23 |  |  |  | 23 |  | 23 | 0 | 0 |  | Yes
Mawsley Play Areas | 0 | 12 |  |  | 12 |  | 12 | 89 | 0 |  | Yes |  |  | ü
West of Desborough - Play Provision | 0 |  |  |  | 0 |  | 0 | 72 | 0 |  | No |  |  | ü
Mawsley - Water Feature | 0 |  |  |  | 0 |  | 0 | 39 | 0 |  | No |  |  | ü
Weekley Glebe - Car Park Extension | 0 |  |  |  | 0 |  | 0 | 28 | 0 |  | No |  |  | ü
Mawsley Community Allotments - Storage | 0 |  |  |  | 0 |  | 0 | 17 | 19 |  | No |  |  | ü
Weekley Glebe - Referee Room | 0 |  |  |  | 0 |  | 0 | 14 | 0 |  | No |  |  | ü
Ise Play Area - Path Provision | 0 |  |  |  | 0 |  | 0 | 12 | 0 |  | No |  |  | ü
Weekley Glebe - Pitch Levelling | 0 |  |  |  | 0 |  | 0 | 11 | 0 |  | No |  |  | ü
KCLL - Leisure Pass Admin System | 0 |  |  |  | 0 |  | 0 | 8 | 0 |  | No |  |  | ü
Grange Estate - Football Facilities | 0 |  |  |  | 0 |  | 0 | 0 | 388 |  | No |  |  | ü
Improvements:
Housing Estates - Parking | 0 | 50 |  |  | 50 |  | 50 | 44 | 52 |  | No |  |  |  |  | ü | [5 empty] | ü
Ise Valley - Barriers & Noise reduction | 0 | 26 | 30 |  | 56 |  | 56 | 0 | 0 |  | Yes |  |  |  |  | ü
Market Towns Env Initiative | 0 | 2 |  |  | 2 |  | 2 | 0 | 0 |  | Yes |  |  |  |  | ü
N'ton Rd Tennis - Floodlights | 0 | 41 |  |  | 41 |  | 41 | 0 | 0 |  | Yes |  |  | ü
Weekley Glebe - Drainage | 0 | 1 |  |  | 1 |  | 1 | 0 | 0 |  | Yes |  |  | ü
Street Scene - various | 0 | 29 |  |  | 29 |  | 29 | 0 | 0 |  | Yes |  |  |  | ü
Other CCTV (A6/HQ Link) | 0 | 5 |  |  | 5 |  | 5 | 0 | 0 |  | No
Rothwell Pool - Refurbishment | 118 |  |  | -118 | 0 |  | 0 | 118 | 117 |  | No |  |  | ü
UDF - Public Realm Enhancement design | 51 |  |  |  | 51 |  | 51 | 0 | 0 |  | No |  |  |  |  | ü
UDF - Laurences factory redevelopment | 17 |  |  |  | 17 |  | 17 | 0 | 0 |  | No |  |  |  |  | ü | ü
Desborough Bowls Club - Clubhouse | 12 |  |  |  | 12 |  | 12 | 92 | 0 |  | No
UDF - Short term parking Desborough | 11 |  |  |  | 11 |  | 11 | 0 | 0 |  | No |  |  |  |  | ü
Waste Education Scheme | 8 |  |  |  | 8 |  | 8 | 113 | 140 |  | Yes |  |  |  | ü
Listed Building/Conservation Grant Scheme | 8 |  |  |  | 8 |  | 8 | 11 | 17 |  | No |  |  |  |  | ü | ü
UDF - Frontage Improvement scheme | 6 |  |  |  | 6 |  | 6 | 8 | 10 |  | No |  |  |  |  | ü | ü
Mobile CCTV - Town Centre | 0 |  |  |  | 0 |  | 0 | 20 | 0 |  | No |  | ü
UDF - Gateway Signage/features | 0 |  |  |  | 0 |  | 0 | 11 | 0 |  | No |  |  |  |  | ü
UDF - Landscape Desborough Town Centre | 0 |  |  |  | 0 |  | 0 | 11 | 6 |  | No |  |  |  |  | ü
UDF - Street Furniture improvements | 0 |  |  |  | 0 |  | 0 | 11 | 6 |  | No |  |  |  |  | ü
Various - Litter Bin Provision | 0 |  |  |  | 0 |  | 0 | 11 | 0 |  | No |  |  |  |  | ü
Museum - Lighting | 0 |  |  |  | 0 |  | 0 | 9 | 0 |  | No |  |  | ü
Contribution for Police Community Team | 0 |  | 15 |  | 15 |  | 15 | 0 | 0 |  | Yes |  | ü
Town Centre Masterplan |  |  |  |  | 0 | 10 | 10 |  |  |  | No |  |  |  |  | ü | ü
Manor Garden - Railings | 0 |  |  |  | 0 |  | 0 | 6 | 0 |  | Yes |  |  |  |  | ü | [5 empty] | ü
Sub Total | 1331 | 312 | 45 | -118 | 1570 | 10 | 1580 | 2092 | 1611 | 0
E-government investment programme
Rolling Programme:
Infrastructure - Ongoing Development | 270 | 0 |  |  | 270 |  | 270 | 40 | 0 |  | Yes | [9 empty] | ü
IEG / CRM / Contact Centre | 0 | 240 |  | 40 | 280 | 172 | 452 | 100 | 0 |  | Yes | [9 empty] | ü
Repair/Replacement:
F.M.S. / Bacs | 215 | 0 |  |  | 215 | 95 | 310 | 0 | 0 |  | Yes | [9 empty] | ü
Council Tax / NNDR | 100 | -26 | 100 |  | 174 |  | 174 | 0 | 0 |  | Yes | ü | [7 empty] | ü | ü
Corporate GIS | 50 | 0 |  |  | 50 | 10 | 60 | 40 | 0 |  | Yes | [9 empty] | ü
Payroll / Pickwick upgrades | 40 | 0 |  |  | 40 | -25 | 15 | 0 | 0 |  | Yes | [9 empty] | ü
Councillors Laptop Replacement | 0 | 0 |  |  | 0 |  | 0 | 72 | 0 |  | No
Equipment Spares - Support | 0 | 0 |  |  | 0 |  | 0 | 10 | 0 |  | No
Replacement - Ageing Printers | 0 | 0 |  |  | 0 |  | 0 | 5 | 0 |  | No | [9 empty] | ü
Replacement burial & crem System | 0 | 0 | 25 |  | 25 |  | 25 | 0 | 0 |  | Yes
Siemens Laptop - Replacement Scheme | 0 | 0 |  |  | 0 |  | 0 | 5 | 0 |  | No
Enhancements:
Remote Working | 57 | 0 |  | -40 | 17 |  | 17 | 0 | 0 |  | Yes | [9 empty] | ü
Corporate Document Management System | 50 | -63 | 50 |  | 37 | 10 | 47 | 90 | 0 |  | Yes | ü | [7 empty] | ü | ü
Planning - Scanners & Printers | 0 | 0 |  |  | 0 |  | 0 | 50 | 0 |  | No | [9 empty] | ü
Video Conferencing | 0 | 0 |  |  | 0 |  | 0 | 5 | 0 |  | No | [9 empty] | ü
Improvements:
Security Testing | 40 | 0 |  |  | 40 |  | 40 | 0 | 0 |  | Yes | [9 empty] | ü
2Mb Circuit | 0 | 0 |  |  | 0 |  | 0 | 6 | 0 |  | No | [9 empty] | ü
Crematorium - Network Connections | 0 | 0 |  |  | 0 |  | 0 | 9 | 0 |  | No | [9 empty] | ü
Planning System | 70 | 159 |  |  | 229 |  | 229 | 0 | 0 |  | Yes | [9 empty] | ü
Housing/Depot System | 70 | 157 |  |  | 227 |  | 227 | 0 | 0 |  | Yes | [9 empty] | ü
Network Improvements | 32 | 0 |  |  | 32 |  | 32 | 0 | 0 |  | Yes | [9 empty] | ü
Website/Intranet Development | 25 | 0 |  |  | 25 |  | 25 | 14 | 0 |  | Yes | [9 empty] | ü
Telephone Handset - Upgrade | 15 | 0 |  |  | 15 |  | 15 | 15 | 0 |  | Yes | [9 empty] | ü
Computer Room - Refurbishment | 0 | 0 |  |  | 0 |  | 0 | 5 | 0 |  | No
Sub Total | 1034 | 467 | 175 | 0 | 1676 | 262 | 1938 | 466 | 0 | 0
Invest To Save Projects | 0 | 30 | 0 | 30 | 60 | 0 | 60 | 200 | 200 | As per Niall | Partly | [9 empty] | ü
CAPITAL PROGRAMME TOTAL | 6610 | 1383 | 253 | -88 | 8158 | -656 | 7502 | 6984 | 5537
Notes on E-Government Schemes:
1. CRM / Contact Centre
The Council is committed to establishing a contact centre approach and had previously agreed to fund a new Contact Management System as a first step toward this. It has been possible to bring the next phase of this project
forward by using part of the e-govt grant that the council received from the Government. The remainder of the e-govt grant is being used to offset the cost of IT schemes already within the programme that the Council
has already agreed. It should be noted that although this scheme is shown within the IT element of the capital programme that some of the costs of the contact centre are non IT related (ie, building / furniture etc…)
2. FMS / Planning / Housing
These back office systems must be replaced by the end of 2004/05 because their license agreements and server platform effectively cease at the end of March 2005. Accordingly, replacement systems are being
implemented to ensure that these business critical support systems continue and that the new systems provide the opportunity for more effective and efficient working whilst also helping deliver the e-govt targets.
Note on E53: Gsoulsby: £22k of 05/06 budget brought fwd into 04/05
Note on E57: Gsoulsby: £11k budget from 05/06 brought fwd into 04/05
Note on E126: Gsoulsby: New budget of £15k approved
Note on E137: Gsoulsby: £100k budget from 05/06 brought fwd into 04/05.
Note on E143: Gsoulsby: New budget of £25k approved
Note on E147: Gsoulsby: £50k of 05/06 budget brought fwd into 04/05
Note on F112: Gsoulsby: Scheme will not start until 05/06 so the budget moved back
Note on H134: Gsoulsby: Increased funding fully offset from the IEG monies from the Govt.
Note on H136: Gsoulsby: Bring Fwd £70k from next year + £25k from pickwick /payroll savings
Note on H138: Gsoulsby: £10k brought fwd from next years budget
Note on H147: Gsoulsby: £10 brought fwd from next years budget
Note on J115: Gsoulsby: £40k of external funding has been pledged to offset some of the scheme cost
Note on K103: Gsoulsby: Partly financed by external grant from sports lottery of £285k