## YEAR 3 SUMMARY SHEET
YEAR 3 (2010 - 2011) GULLY CLEANSING SCHEDULE SUMMARY SHEET
| 2010 | [23 empty] | 2011
| May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
Area | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Corby | 33 | 0 | 0 | 0 | 445 | 190 | 0 | 1102 | 0 | 0 | 3220 | 795 | 0 | 0 | 0 | 0 | 1046 | 1697 | 0 | 624 | 0 | 0 | 1577 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12090
Daventry | 0 | 479 | 309 | 11 | 801 | 0 | 144 | 3970 | 237 | 71 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 11 | 913 | 0 | 144 | 1177 | 0 | 71 | 1689 | 0 | 0 | 2067 | 550 | 80 | 1987 | 0 | 14791
East Northamptonshire | 8 | 0 | 0 | 17 | 421 | 0 | 14 | 107 | 227 | 22 | 0 | 0 | 44 | 0 | 0 | 35 | 0 | 0 | 8 | 417 | 0 | 17 | 317 | 0 | 14 | 36 | 72 | 22 | 203 | 486 | 44 | 500 | 701 | 35 | 1398 | 0 | 5165
Kettering | 0 | 1114 | 1096 | 944 | 411 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 53 | 872 | 510 | 107 | 425 | 600 | 50 | 1315 | 0 | 116 | 1190 | 0 | 0 | 1393 | 0 | 0 | 1216 | 0 | 43 | 1595 | 0 | 107 | 0 | 0 | 13207
Northampton | 1 | 170 | 682 | 30 | 445 | 0 | 0 | 840 | 0 | 26 | 1270 | 0 | 21 | 2462 | 500 | 1 | 1998 | 500 | 0 | 1998 | 1872 | 30 | 2000 | 0 | 0 | 2289 | 0 | 26 | 3412 | 0 | 21 | 1179 | 0 | 0 | 1302 | 176 | 23251
South Northamptonshire | 130 | 249 | 169 | 0 | 3 | 0 | 25 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 130 | 24 | 500 | 0 | 31 | 0 | 25 | 102 | 342 | 31 | 113 | 0 | 0 | 0 | 0 | 63 | 1156 | 123 | 3310
Wellingborough | 42 | 2387 | 150 | 0 | 2816 | 0 | 0 | 0 | 0 | 46 | 973 | 0 | 0 | 2212 | 49 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8763
Total | 214 | 4399 | 2406 | 1002 | 5342 | 190 | 183 | 6019 | 464 | 246 | 5463 | 795 | 118 | 5546 | 1059 | 286 | 3469 | 2797 | 211 | 4378 | 2372 | 174 | 6028 | 0 | 183 | 6358 | 414 | 215 | 6633 | 486 | 108 | 5341 | 1251 | 285 | 5843 | 299 | 80577
Grand Total | 7019 |  |  | 6534 |  |  | 6666 |  |  | 6504 |  |  | 6723 |  |  | 6552 |  |  | 6961 |  |  | 6202 |  |  | 6955 |  |  | 7334 |  |  | 6700 |  |  | 6427 |  |  | 80577
|  |  | May | June | July | August | September | October | November | December | January | February | March | April
| Corby |  | 33 | 635 | 1102 | 4015 | 0 | 2743 | 624 | 1577 | 1361 | 0 | 0 | 0 |  | 12090
| Daventry |  | 788 | 812 | 4351 | 71 | 0 | 80 | 0 | 924 | 1321 | 1760 | 2617 | 2067 |  | 14791
| East N Hants |  | 8 | 438 | 348 | 22 | 44 | 35 | 425 | 334 | 122 | 711 | 1245 | 1433 |  | 5165
| Kettering |  | 2210 | 1355 | 0 | 50 | 1435 | 1132 | 1365 | 1306 | 1393 | 1216 | 1638 | 107 |  | 13207
| Northampton |  | 853 | 475 | 840 | 1296 | 2983 | 2499 | 3870 | 2030 | 2289 | 3438 | 1200 | 1478 |  | 23251
| South N Hants |  | 548 | 3 | 25 | 31 | 0 | 63 | 654 | 31 | 469 | 144 | 0 | 1342 |  | 3310
| Wellingborough |  | 2579 | 2816 | 0 | 1019 | 2261 | 0 | 23 | 0 | 0 | 65 | 0 | 0 |  | 8763
|  |  | 7019 | 6534 | 6666 | 6504 | 6723 | 6552 | 6961 | 6202 | 6955 | 7334 | 6700 | 6427 |  | 80577

## CORBY
Corby Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
East Carlton | 112 |  |  |  |  | 61 | 51 | [30 empty] | 112
Middleton | 119 |  |  |  |  | 64 | 55 | [30 empty] | 119
Cottingham | 291 |  |  |  |  | 226 | 65 | [30 empty] | 291
Rockingham | 113 |  |  |  |  | 94 | 19 | [30 empty] | 113
Gretton | 243 | [36 empty] | 0
Weldon | 999 | [7 empty] | 826 | [28 empty] | 826
Stanion | 475 | [7 empty] | 276 | [28 empty] | 276
Corby 1 | 2596 | [10 empty] | 2540 | 56 | [24 empty] | 2596
Corby 2 | 1419 | [10 empty] | 680 | 739 | [24 empty] | 1419
Corby 3 | 559 | [17 empty] | 534 | [18 empty] | 534
Corby 4 | 917 | 33 | [15 empty] | 33 | 849 | [18 empty] | 915
Corby 5 | 438 | [16 empty] | 337 | [19 empty] | 337
Corby 6 | 990 | [16 empty] | 676 | 314 | [18 empty] | 990
Corby 7 | 666 | [19 empty] | 624 | [16 empty] | 624
Corby 8 | 1728 | [22 empty] | 1577 | [13 empty] | 1577
Corby 9 | 655 | [25 empty] | 561 | [10 empty] | 561
Corby 10 | 800 | [25 empty] | 800 | [10 empty] | 800
TOTAL GULLIES | 13120 | 33 | 0 | 0 | 0 | 445 | 190 | 0 | 1102 | 0 | 0 | 3220 | 795 | 0 | 0 | 0 | 0 | 1046 | 1697 | 0 | 624 | 0 | 0 | 1577 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12090

## DAVENTRY
Daventry Area Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Flore | 283 |  | 118 | 165 | [33 empty] | 283
Brington | 145 |  | 87 | 58 | [33 empty] | 145
Althorp | 24 |  | 24 | 0 | [33 empty] | 24
Harlestone | 101 |  | 101 | 0 | [33 empty] | 101
Church Brampton | 47 |  | 32 | 15 | [33 empty] | 47
Chapel Brampton | 188 |  | 117 | 71 | [33 empty] | 188
Pitsford | 225 |  |  |  | 11 | 144 | [16 empty] | 11 | [14 empty] | 166
Boughton | 374 |  |  |  |  | 231 | [31 empty] | 231
Moulton | 659 |  |  |  |  | 293 | [31 empty] | 293
Brockhall | 5 |  |  |  |  | 5 | [31 empty] | 5
Stowe IX Churches | 35 |  |  |  |  | 3 | [31 empty] | 3
Dodford | 97 |  |  |  |  | 82 | [31 empty] | 82
Naseby | 223 |  |  |  |  | 43 | [31 empty] | 43
Clipston | 189 | [7 empty] | 98 | [28 empty] | 98
Great Oxendon | 105 | [7 empty] | 105 | 0 | [27 empty] | 105
Arthingworth | 123 | [7 empty] | 118 | 5 | [27 empty] | 123
East Farndon | 71 | [7 empty] | 12 | [28 empty] | 12
Marston Trussell | 27 | [7 empty] | 17 | 10 | [27 empty] | 27
Sibbertoft | 62 | [7 empty] | 7 | [28 empty] | 7
Sulby | 25 | [7 empty] | 25 | 0 | [27 empty] | 25
Welford | 229 | [7 empty] | 87 | [28 empty] | 87
Stanford | 13 | [7 empty] | 3 | 10 | [27 empty] | 13
Clay Coton | 5 | [7 empty] | 5 | 0 | [27 empty] | 5
Yelvertoft | 178 | [6 empty] | 48 | 94 | [16 empty] | 48 | [11 empty] | 190
Crick | 485 | [6 empty] | 26 | 260 | [16 empty] | 26 | [11 empty] | 312
West Haddon | 258 | [7 empty] | 258 | [28 empty] | 258
Ravensthorpe | 223 | [7 empty] | 223 | [28 empty] | 223
Hollowell | 183 | [7 empty] | 182 | [28 empty] | 182
Guilsborough | 217 | [7 empty] | 216 | [28 empty] | 216
Cold Ashby | 190 | [6 empty] | 17 | 173 | [16 empty] | 17 | [11 empty] | 207
Elkington | 18 | [7 empty] | 18 | [28 empty] | 18
Thornby | 64 | [7 empty] | 33 | 31 | [27 empty] | 64
Cottesbrooke | 72 | [7 empty] | 72 | 0 | [27 empty] | 72
Creaton | 119 | [7 empty] | 119 | 0 | [27 empty] | 119
Spratton | 408 | [7 empty] | 408 | 0 | [27 empty] | 408
Holdenby | 33 | [7 empty] | 33 | 0 | [27 empty] | 33
East Haddon | 238 | [6 empty] | 53 | 185 | 0 | [15 empty] | 53 | [11 empty] | 291
Long Buckby | 1231 | [7 empty] | 1158 | 73 | [27 empty] | 1231
Watford | 169 | [7 empty] | 61 | 108 | [27 empty] | 169
Welton | 277 | [25 empty] | 150 | [10 empty] | 150
Ashby St. Ledgers | 55 | [25 empty] | 9 | [10 empty] | 9
Kilsby | 409 | [25 empty] | 409 | [10 empty] | 409
Barby | 400 | [25 empty] | 400 | [10 empty] | 400
Braunston | 435 | [25 empty] | 209 | [10 empty] | 209
Daventry 1 | 975 | [22 empty] | 913 | [13 empty] | 913
Daventry 2 | 714 | [9 empty] | 69 | [17 empty] | 69 | 565 | [7 empty] | 703
Daventry 3 | 807 | [9 empty] | 2 | [17 empty] | 2 | 714 | [7 empty] | 718
Daventry 4 | 1164 | [28 empty] | 410 | [7 empty] | 410
Daventry 5 | 1296 | [31 empty] | 958 |  |  |  |  | 958
Norton | 68 | [31 empty] | 64 | 4 |  |  |  | 68
Whilton | 65 | [31 empty] | 58 | 8 |  |  |  | 66
Holcot | 86 | [31 empty] | 67 | 19 |  |  |  | 86
Hannington | 174 | [31 empty] | 165 | 9 |  |  |  | 174
Walgrave | 111 | [31 empty] | 111 |  |  |  |  | 111
Old | 103 | [31 empty] | 103 |  |  |  |  | 103
Scaldwell | 47 | [31 empty] | 47 |  |  |  |  | 47
Brixworth | 1004 | [31 empty] | 494 | 510 |  |  |  | 1004
Lamport | 136 | [34 empty] | 131 |  | 131
Draughton | 12 | [34 empty] | 9 |  | 9
Kelmarsh | 68 | [34 empty] | 68 |  | 68
Preston Capes | 26 | [34 empty] | 24 |  | 24
Canons Ashby | 17 | [34 empty] | 17 |  | 17
Woodford Cum Membris | 617 | [34 empty] | 88 |  | 88
Byfield | 228 | [34 empty] | 103 |  | 103
Weedon Bec | 579 | [15 empty] | 42 | [17 empty] | 42 | 467 |  | 551
Overstone | 125 | [34 empty] | 120 |  | 120
Everdon | 94 | [34 empty] | 94 |  | 94
Fawsley | 1 | [34 empty] | 1 |  | 1
Newnham | 212 | [34 empty] | 212 |  | 212
Badby | 190 | [34 empty] | 190 |  | 190
Staverton | 177 | [34 empty] | 177 |  | 177
Catesby | 1 | [34 empty] | 1 |  | 1
Hellidon | 39 | [34 empty] | 39 |  | 39
Charwelton | 56 | [15 empty] | 38 | [17 empty] | 38 | 18 |  | 94
Maidwell | 60 | [34 empty] | 60 |  | 60
Haselbech | 29 | [34 empty] | 29 |  | 29
Lilbourne | 74 | [34 empty] | 74 |  | 74
Winwick | 20 | [34 empty] | 20 |  | 20
Farthingstone | 45 | [34 empty] | 45 |  | 45
TOTAL GULLIES | 18337 | 0 | 479 | 309 | 11 | 801 | 0 | 144 | 3970 | 237 | 71 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 11 | 913 | 0 | 144 | 1177 | 0 | 71 | 1689 | 0 | 0 | 2067 | 550 | 80 | 1987 | 0 | 14791

## EAST NORTHANTS
East Northants Area Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Woodford | 256 |  |  |  |  | 10 | [31 empty] | 10
Newton Bromswold | 36 |  |  |  |  | 36 | [31 empty] | 36
Higham Ferrers | 1007 |  |  |  |  | 136 | [31 empty] | 136
Rushden 1 | 1104 |  |  |  |  | 92 | [31 empty] | 92
Rushden 2 | 565 |  |  |  |  | 147 | [31 empty] | 147
Rushden 3 | 348 | [6 empty] | 14 | 107 | 227 | [15 empty] | 14 | [11 empty] | 362
Rushden 4 | 213 | 8 | [17 empty] | 8 | 80 | [16 empty] | 96
Rushden 5 | 723 | [19 empty] | 105 | [16 empty] | 105
Rushden 6 | 303 | [36 empty] | 0
Rushden 7 | 392 | [19 empty] | 219 | [16 empty] | 219
Rushden 8 | 153 | [36 empty] | 0
Rushden 9 | 274 | [36 empty] | 0
Rushden 10 | 255 | [19 empty] | 13 | [16 empty] | 13
Benefield | 168 | [22 empty] | 87 | [13 empty] | 87
Deenethorpe | 29 | [22 empty] | 4 | [13 empty] | 4
Deene | 20 | [22 empty] | 20 | [13 empty] | 20
Bulwick | 166 | [22 empty] | 45 | [13 empty] | 45
Blatherwycke | 31 | [36 empty] | 0
Laxton | 80 |  |  |  | 17 | [17 empty] | 17 | 23 | [13 empty] | 57
Harringworth | 204 | [36 empty] | 0
Wakerley | 56 | [22 empty] | 13 | [13 empty] | 13
Duddington-with-Fineshade | 148 | [22 empty] | 38 | [13 empty] | 38
Collyweston | 241 | [22 empty] | 49 | [13 empty] | 49
Easton on the Hill | 278 | [22 empty] | 30 | [13 empty] | 30
King's Cliffe | 271 | [36 empty] | 0
Apethorpe | 52 | [36 empty] | 0
Nassington | 159 | [36 empty] | 0
Yarwell | 102 | [22 empty] | 8 | [13 empty] | 8
Fotheringhay | 36 | [36 empty] | 0
Woodnewton | 108 | [25 empty] | 36 | 72 | [9 empty] | 108
Southwick | 45 | [9 empty] | 17 | [17 empty] | 17 | 7 | 21 | [6 empty] | 62
Glapthorn | 71 | [28 empty] | 25 | 46 | [6 empty] | 71
Cotterstock | 29 | [9 empty] | 5 | [17 empty] | 5 | 24 | 0 | [6 empty] | 34
Tansor | 152 | [29 empty] | 152 | [6 empty] | 152
Warmington | 277 | [28 empty] | 10 | 267 | [6 empty] | 277
Oundle | 1018 | [28 empty] | 137 | [7 empty] | 137
Stoke Doyle | 17 | [31 empty] | 14 | 3 |  |  |  | 17
Lowick | 187 | [32 empty] | 187 |  |  |  | 187
Sudborough | 126 | [31 empty] | 85 | 41 |  |  |  | 126
Brigstock | 487 | [12 empty] | 44 | [17 empty] | 44 | 190 | 253 |  |  |  | 531
Ashton Wold | 81 | [31 empty] | 13 | 68 |  |  |  | 81
Polebrook | 74 | [31 empty] | 49 | 25 |  |  |  | 74
Lutton | 42 | [32 empty] | 42 |  |  |  | 42
Hemington | 46 | [32 empty] | 46 |  |  |  | 46
Thorpe Achurch | 163 | [31 empty] | 148 | 15 |  |  |  | 163
Thurning | 21 | [32 empty] | 21 |  |  |  | 21
Luddington | 1 | [31 empty] | 1 |  |  |  |  | 1
Clopton | 37 | [34 empty] | 37 |  | 37
Lilford-Cum-Wigsthorpe | 41 | [34 empty] | 41 |  | 41
Barnwell | 215 | [34 empty] | 65 |  | 65
Pilton | 23 | [34 empty] | 2 |  | 2
Wadenhoe | 33 | [36 empty] | 0
Aldwincle | 99 | [36 empty] | 0
Titchmarsh | 272 | [34 empty] | 18 |  | 18
Thrapston | 849 | [34 empty] | 535 |  | 535
Irthlingborough | 1004 | [34 empty] | 188 |  | 188
Islip | 292 | [34 empty] | 85 |  | 85
Denford | 58 | [34 empty] | 4 |  | 4
Ringstead | 331 | [15 empty] | 35 | [17 empty] | 35 | 36 |  | 106
Raunds | 1187 | [34 empty] | 83 |  | 83
Stanwick | 231 | [34 empty] | 231 |  | 231
Hargrave | 65 | [34 empty] | 65 |  | 65
Chelveston cum Caldecott | 147 | [36 empty] | 0
Great Addington | 60 | [34 empty] | 3 |  | 3
Little Addington | 54 | [36 empty] | 0
Twywell | 93 | [34 empty] | 5 |  | 5
TOTAL GULLIES | 15706 | 8 | 0 | 0 | 17 | 421 | 0 | 14 | 107 | 227 | 22 | 0 | 0 | 44 | 0 | 0 | 35 | 0 | 0 | 8 | 417 | 0 | 17 | 317 | 0 | 14 | 36 | 72 | 22 | 203 | 486 | 44 | 500 | 701 | 35 | 1398 | 0 | 5165

## KETTERING
Kettering Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Thorpe Malsor | 30 |  | 30 | 0 | [33 empty] | 30
Cransley | 102 |  | 46 | 56 | [33 empty] | 102
Broughton | 449 |  | 284 | [34 empty] | 284
Pytchley | 305 |  | 305 | 0 | [33 empty] | 305
Barton Seagrave | 719 |  | 386 | [34 empty] | 386
Braybrooke | 144 |  |  | 54 | [33 empty] | 54
Rothwell | 1548 |  | 63 | 986 | [18 empty] | 63 | [14 empty] | 1112
Stoke Albany | 171 |  |  |  | 61 | 110 | [31 empty] | 171
Brampton Ash | 30 |  |  |  | 30 | 0 | [31 empty] | 30
Dingley | 307 |  |  |  | 173 | 134 | [31 empty] | 307
Sutton Bassett | 59 |  |  |  | 51 | 8 | [31 empty] | 59
Weston by Welland | 73 |  |  |  | 71 | 2 | [31 empty] | 73
Ashley | 54 |  |  |  | 54 | 0 | [31 empty] | 54
Wilbarston | 206 |  |  |  | 39 | [32 empty] | 39
Newton and Little Oakley | 161 |  |  |  | 36 | [32 empty] | 36
Geddington | 308 |  |  |  | 120 | [32 empty] | 120
Rushton | 250 |  |  |  | 21 | [32 empty] | 21
Cranford | 208 |  |  |  | 102 | 104 | [31 empty] | 206
Grafton Underwood | 73 |  |  |  | 72 | 1 | [31 empty] | 73
Warkton | 38 |  |  |  |  | 38 | [31 empty] | 38
Weekley | 128 |  |  |  | 114 | 14 | [31 empty] | 128
Kettering 1 | 1089 | [15 empty] | 64 | 425 | 600 | [15 empty] | 64 |  |  | 1153
Kettering 2 | 1403 | [12 empty] | 21 | 872 | 510 | [6 empty] | 21 | [14 empty] | 1424
Kettering 3 | 1032 | [19 empty] | 807 | [16 empty] | 807
Kettering 4 | 563 | [9 empty] | 50 | [8 empty] | 50 | 508 | [16 empty] | 608
Kettering 5 | 540 | [12 empty] | 12 | [8 empty] | 12 | 528 | [13 empty] | 552
Kettering 6 | 508 | [12 empty] | 20 | [8 empty] | 20 | 488 | [13 empty] | 528
Kettering 7 | 174 | [22 empty] | 174 | [13 empty] | 174
Kettering 8 | 513 | [15 empty] | 43 | [14 empty] | 43 | 470 |  | 43 |  |  | 599
Kettering 9 | 817 | [25 empty] | 817 | [10 empty] | 817
Kettering 10 | 669 | [25 empty] | 576 | [10 empty] | 576
Burton Latimer | 1104 | [28 empty] | 1059 | [7 empty] | 1059
Orton | 19 | [28 empty] | 19 | [7 empty] | 19
Loddington | 138 | [28 empty] | 138 | [7 empty] | 138
Desborough | 1287 | [31 empty] | 1011 |  |  |  |  | 1011
Harrington | 114 | [31 empty] | 114 |  |  |  |  | 114
TOTAL GULLIES | 15333 | 0 | 1114 | 1096 | 944 | 411 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 53 | 872 | 510 | 107 | 425 | 600 | 50 | 1315 | 0 | 116 | 1190 | 0 | 0 | 1393 | 0 | 0 | 1216 | 0 | 43 | 1595 | 0 | 107 | 0 | 0 | 13207

## NORTHAMPTON
Northampton Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Collingtree | 201 | [36 empty] | 0
Collingtree | 201 |  | 0 | 201 | [33 empty] | 201
Hardingstone | 651 |  | 170 | 481 | [33 empty] | 651
Wootton | 3735 |  |  |  | 30 | 445 |  |  | 440 | [13 empty] | 30 | [14 empty] | 945
Duston | 2396 | [7 empty] | 400 |  |  | 450 | [25 empty] | 850
Northampton East | 5888 | [9 empty] | 26 | 820 |  |  | 2462 | [13 empty] | 26 | [8 empty] | 3334
Northampton North | 8869 | 1 | [13 empty] | 500 | 1 | 1998 | 500 |  | 1998 | 1872 |  | 2000 | [13 empty] | 8870
Northampton South | 3437 | [25 empty] | 2289 | [10 empty] | 2289
Northampton West | 5055 | [12 empty] | 21 | [15 empty] | 3412 |  | 21 | [5 empty] | 3454
Northampton Central | 1122 | [31 empty] | 954 |  |  |  |  | 954
Great Houghton | 331 | [31 empty] | 117 |  |  |  |  | 117
Upton | 123 | [31 empty] | 108 |  |  |  |  | 108
Billing | 1478 | [34 empty] | 1302 | 176 | 1478
0
TOTAL GULLIES | 33487 | 1 | 170 | 682 | 30 | 445 | 0 | 0 | 840 | 0 | 26 | 1270 | 0 | 21 | 2462 | 500 | 1 | 1998 | 500 | 0 | 1998 | 1872 | 30 | 2000 | 0 | 0 | 2289 | 0 | 26 | 3412 | 0 | 21 | 1179 | 0 | 0 | 1302 | 176 | 23251
PARISH CONTAINING HOTSPOT LOCATION
Billing | ADDED TO SCHEDULES

## SOUTH NORTHANTS
South Northants Gully Emptying Programme 2010-2011
Parish |  | 2010 | [23 empty] | 2011
|  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Old Stratford | 331 | 44 | 118 | 169 | [15 empty] | 44 | [17 empty] | 375
Wicken | 131 |  | 0 | [34 empty] | 0
Deanshanger | 681 | 54 | 111 | [16 empty] | 54 | [17 empty] | 219
Potterspury | 247 |  | 0 | [34 empty] | 0
Cosgrove | 155 |  | 13 | [34 empty] | 13
Yardley Gobion | 294 |  | 7 | [34 empty] | 7
Grafton Regis | 81 |  |  |  |  | 0 | [31 empty] | 0
Paulerspury | 145 |  |  |  |  | 0 | [31 empty] | 0
Whittlebury | 184 |  |  |  |  | 0 | [31 empty] | 0
Syresham | 182 |  |  |  |  | 0 | [31 empty] | 0
Evenley | 210 |  |  |  |  | 0 | [31 empty] | 0
Croughton | 103 |  |  |  |  | 0 | [31 empty] | 0
Aynho | 184 |  |  |  |  | 3 | [31 empty] | 3
Kings Sutton | 352 | [7 empty] | 0 | [28 empty] | 0
Newbottle | 78 | [7 empty] | 0 | [28 empty] | 0
Hinton-in-The Hedges | 51 | [7 empty] | 0 | [28 empty] | 0
Brackley | 2337 | 32 | [17 empty] | 32 | 24 | 500 | [15 empty] | 588
Whitfield | 36 | [22 empty] | 10 | [13 empty] | 10
Silverstone | 459 | [22 empty] | 12 | [13 empty] | 12
Greens Norton | 282 | [22 empty] | 9 | [13 empty] | 9
Blakesley | 85 | [22 empty] | 0 | [13 empty] | 0
Woodend | 49 | [22 empty] | 0 | [13 empty] | 0
Bradden | 30 | [22 empty] | 0 | [13 empty] | 0
Slapton | 39 | [22 empty] | 0 | [13 empty] | 0
Abthorpe | 63 | [22 empty] | 0 | [13 empty] | 0
Wappenham | 50 | [22 empty] | 0 | [13 empty] | 0
Weston and Weedon | 53 | [22 empty] | 0 | [13 empty] | 0
Helmdon | 120 | [22 empty] | 0 | [13 empty] | 0
Radstone | 3 | [22 empty] | 0 | [13 empty] | 0
Greatworth | 118 | [25 empty] | 1 | 117 | [9 empty] | 118
Marston St. Lawrence | 34 | [25 empty] | 0 | 34 | [9 empty] | 34
Thenford | 12 | [25 empty] | 0 | 12 | [9 empty] | 12
Farthinghoe | 69 | [6 empty] | 25 | [17 empty] | 25 | 28 | 16 | [9 empty] | 94
Middleton Cheney | 663 | [25 empty] | 7 | [10 empty] | 7
Warkworth | 27 | [25 empty] | 0 | 27 | [9 empty] | 27
Overthorpe | 52 | [25 empty] | 0 | 52 | [9 empty] | 52
Chacombe | 127 | [25 empty] | 43 | 84 | [9 empty] | 127
Thorpe Mandeville | 61 | [25 empty] | 21 | [10 empty] | 21
Sulgrave | 43 | [25 empty] | 2 | [10 empty] | 2
Culworth | 74 | [25 empty] | 0 | [10 empty] | 0
Adstone | 25 | [28 empty] | 2 | [7 empty] | 2
Maidford | 40 | [28 empty] | 3 | [7 empty] | 3
Litchborough | 52 | [28 empty] | 0 | [7 empty] | 0
Cold Higham | 32 | [28 empty] | 0 | [7 empty] | 0
Nether Heyford | 268 | [28 empty] | 2 | [7 empty] | 2
Upper Heyford | 127 | [28 empty] | 3 | [7 empty] | 3
Bugbrooke | 535 | [9 empty] | 31 | [17 empty] | 31 | 61 | [7 empty] | 123
Rothersthorpe | 79 | [28 empty] | 0 | [7 empty] | 0
Milton Malsor | 186 | [28 empty] | 42 | [7 empty] | 42
Gayton | 163 | [28 empty] | 0 | [7 empty] | 0
Tiffield | 102 | [28 empty] | 0 | [7 empty] | 0
Pattishall | 238 | [28 empty] | 0 | [7 empty] | 0
Easton Neston | 39 | [28 empty] | 0 | [7 empty] | 0
Towcester | 1525 | [34 empty] | 417 |  | 417
Shutlanger | 43 | [15 empty] | 2 | [17 empty] | 2 | 10 |  | 14
Stoke Bruerne | 160 | [15 empty] | 7 | [17 empty] | 7 | 13 |  | 27
Blisworth | 364 | [15 empty] | 1 | [17 empty] | 1 | 13 |  | 15
Courteenhall | 73 | [34 empty] | 2 |  | 2
Roade | 447 | [15 empty] | 21 | [17 empty] | 21 | 10 |  | 52
Ashton | 65 | [34 empty] | 38 |  | 38
Hartwell | 275 | [15 empty] | 32 | [17 empty] | 32 | 101 |  | 165
Quinton | 35 | [34 empty] | 13 |  | 13
Hackleton | 310 | [34 empty] | 14 |  | 14
Brafield on the Green | 217 | [34 empty] | 0 |  | 0
Denton | 161 | [34 empty] | 0 |  | 0
Yardley Hastings | 220 | [34 empty] | 93 |  | 93
Castle Ashby | 49 | [34 empty] | 0 |  | 0
Cogenhoe and Whiston | 229 | [34 empty] | 6 |  | 6
Little Houghton | 150 | [34 empty] | 0 |  | 0
Kislingbury | 247 | [34 empty] | 10 |  | 10
Harpole | 401 | [34 empty] | 322 |  | 322
Moreton Pinkney | 50 | [34 empty] | 0 |  | 0
Eydon | 68 | [34 empty] | 29 | 39 | 68
Boddington | 150 | [34 empty] | 0 |  | 0
Aston le Walls | 91 | [34 empty] | 7 | 84 | 91
Chipping Warden | 194 | [34 empty] | 58 |  | 58
Alderton | 86 | [34 empty] | 0 |  | 0
Grange Park | 151 | [34 empty] | 0 |  | 0
TOTAL GULLIES | 15942 | 130 | 249 | 169 | 0 | 3 | 0 | 25 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 130 | 24 | 500 | 0 | 31 | 0 | 25 | 102 | 342 | 31 | 113 | 0 | 0 | 0 | 0 | 63 | 1156 | 123 | 3310

## WELLINGBOROUGH
Wellingborough Area Gully Emptying Programme 2010-2011
Parish | Total | 2010 | [23 empty] | 2011
| Gullies | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April |  |  | Total
|  | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year | 6 month | 1 year | 2 year
Orlingbury | 84 |  | 4 | [34 empty] | 4
Isham | 237 | 19 | 160 | [25 empty] | 19 | [8 empty] | 198
Wellingborough 1 | 920 |  | 707 | [34 empty] | 707
Wellingborough 2 | 857 |  | 707 | 150 | [33 empty] | 857
Wellingborough 3 | 1211 |  | 809 | [34 empty] | 809
Wellingborough 4 | 663 |  |  |  |  | 650 | [31 empty] | 650
Wellingborough 5 | 734 |  |  |  |  | 676 | [31 empty] | 676
Wellingborough 6 | 715 |  |  |  |  | 691 | [31 empty] | 691
Wellingborough 7 | 465 |  |  |  |  | 438 | [31 empty] | 438
Wellingborough 8 | 466 |  |  |  |  | 361 | [31 empty] | 361
Wellingborough 9 | 574 | [9 empty] | 35 | 539 | [16 empty] | 35 | [8 empty] | 609
Wellingborough 10 | 409 | [9 empty] | 11 | 381 | [16 empty] | 11 | [8 empty] | 403
Easton Maudit | 7 | [10 empty] | 0 | [25 empty] | 0
Bozeat | 532 | [13 empty] | 465 | [22 empty] | 465
Strixton | 53 | [10 empty] | 53 | [25 empty] | 53
Wollaston | 653 | [13 empty] | 396 | [22 empty] | 396
Wilby | 96 | [13 empty] | 0 | [22 empty] | 0
Irchester | 715 | [13 empty] | 279 | [22 empty] | 279
Finedon | 635 | [13 empty] | 276 | [22 empty] | 276
Great Harrowden | 69 | [13 empty] | 42 | 27 | [21 empty] | 69
Little Harrowden | 207 | [13 empty] | 90 | [22 empty] | 90
Hardwick | 10 | [13 empty] | 0 | [22 empty] | 0
Mears Ashby | 76 | [13 empty] | 61 | 15 | [21 empty] | 76
Sywell | 240 | [13 empty] | 233 | 7 | [21 empty] | 240
Ecton | 66 | [13 empty] | 2 | [22 empty] | 2
Earls Barton | 863 | 23 | [12 empty] | 330 |  |  |  |  | 23 | [17 empty] | 376
Great Doddington | 247 | [13 empty] | 33 | [22 empty] | 33
Grendon | 77 | [13 empty] | 5 | [22 empty] | 5
TOTAL GULLIES | 11881 | 42 | 2387 | 150 | 0 | 2816 | 0 | 0 | 0 | 0 | 46 | 973 | 0 | 0 | 2212 | 49 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8763