Stages in the Preparation of the Site Specific Proposals LDD

STAGE						TIMETABLE

Issues Paper Consultation: This consultation discussed issues to be addressed in the Site Specific Proposals LDD.

Consultation on the Issues Paper took place in March/ April 2009

Background papers: provide evidence base for the option paper. To be updated following the consultation on options to take account of representations made and additional evidence gathered.

Current Stage

To be confirmed following JPC committee

Consultation on Options: Present range of options which to address the issues identified through Issues Paper consultation. Will indicate which are the preferred options.

Preparation of Proposed Submission Plan: Information gathered through earlier consultation will be used to prepare the Proposed Submission Plan.

July/August 2012

Consultation on Proposed Submission Plan: Six week consultation on the draft plan prior to submission of Plan to Secretary of State

October 2012

December 2012

Submission of Plan to the Secretary of State

Independent Examination

Adoption

March 2013