## Route Map EK
|  | 2013 | [7 empty] | 2014 | [11 empty] | 2015
Workstream | Description | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Funding Due Diligence
| SEMLEP | 2013 May: offer rec'd; 2013 June: shared DD; 2013 August: Contractual offer; 2014 February: draw SEMLEP for Jn F works
| NEP | 2013 June: shared DD; 2013 August: Contractual offer; 2014 February: draw NEP for Junction E works
| HCA LIF | 2013 June: offer rec'd; 2013 July: DD; 2013 August: Contractual offer; 2013 September: draw for Jn F roads and attenuation; 2014 January: draw for school; 2015 February: Last Qualifying Expenditure
Planning
| s106 (ABL) | 2013 May: s106 agreed; 2013 June: completed
| s106 other land | 2013 July: HLM s106; 2013 August: Persimmon s106; 2013 September: TW s106
| Variation/simplification of conditions | 2013 May: pre app discussions; 2013 July: ABL submission; 2013 August: consultation etc.; 2013 November: committee
| Generic conditions discharge | 2013 May: Persimmon and TW discussion and collaboration; 2013 August: preparation of reports; 2013 October: RMA sub; 2014 January: committee
| Specific conditions discharge | 2013 May: DWH; 2013 June: Persimmon
| RMA (Infrastructure) Jn D | 2013 May: consultation etc.; 2013 November: committee
| RMA (I) attenuation | 2013 August: RMA sub ABL; 2013 November: committee
| RMA (I) Jn E | 2013 August: RMA sub ABL; 2013 November: committee
| RMA (I) Jn F | 2013 August: RMA sub ABL; 2013 November: committee
| RMA (I) PS2 | 2014 May: RMA sub HLM; 2014 August: committee
| RMA DWH/Barratt | 2013 May: consultation etc.; 2013 November: committee
| RMA Persimmon | 2013 May: consultation etc; 2013 November: committee
| RMA ABL | 2013 November: RMA sub ABL; 2014 March: committee
RMA TW???
Delivery
| Junction D | 2013 May: HLM design; 2013 June: RMA submitted; 2013 July: consultation
[8 empty] | committee |  | DWH commence roads |  | DWH commence house building |  |  | attenuation available
| School PS2 | 2013 October: HLM design cost and agree with NCC; 2014 January: final design; 2014 February: RMA submission
[14 empty] | committee |  | Construction of PS2 school and playing fields | [13 empty] | PS 2 available
| Junction E | 2013 May: PBA designand costing; 2013 July: final design; 2013 August: RMA submission
|  |  | TW discussions | TW collaboration | joint submission? |  |  | committee |  |  | contract commence 16 weeks |  |  | TW site access | ABL site access | District Centre access
| Junction F | 2013 May: PBA design, modelling and costing; 2013 July: final design; 2013 August: RMA submission
|  |  | Persimmon discussion and collaboration |  | joint submission |  |  | committee |  |  | contract commence 20 weeks |  |  |  | PersimmonEmployment and ABL site access
| Attenuation Basin | 2013 May: PBA design and costings; 2013 July: final design; 2013 August: RMA submission; 2013 November: land out of farming
[5 empty] | ABL submission |  |  | committee |  |  | contract commence 12 weeks |  |  | surface water solution available
| Foul Water strategic sol'n | 2013 May: PBA and AWSL design and cost; 2013 July: Joint discussions and instruction to AWSL; 2013 August: AWSL requisition, planning; 2013 December: committee??; 2014 February: strategic main upgrade
| Distict Centre | 2013 November: marketing of DC
[10 empty] | RMA DC2 pt |  |  | committee | [6 empty] | RMA DC 1 or 2 pt |  |  | committee
[14 empty] | deliver DC2 (pt) | [10 empty] | deliver DC1 or 2 pt
| Onsite Roading | 2013 December: PBA design and cost on site roads ready for DC RMAs
[13 empty] | RMA road extension (1) | [8 empty] | RMA road extension (2)
[19 empty] | Contract road extension 2015 | [9 empty] | Contract Road extension 2016
Strategic
| Junction 10a | 2013 May: Survey, design, cost, business case to Government
| WWA | 2013 May: Survey, design, cost, business case to County and Government