Please note this is subject to change as there are a number of items that have on going technical work and agreements to be completed and to be put in place.

March 2013

April 2013

May 2013

June 2013

July 2013

August 2013

September 2013

October 2013

November 2013

December 2013

Extension of Time applications submit (hold on to until Autumn)

Outline approval kept alive with the submission of 2 RMA (Hallam & Persimmon)

S106 renegotiated

Consultations underway. Access D being examined.

Full application – Taylor Wimpey

Drainage strategy being examined in detail for foul sewage

A14 Junction 10a design work starting. Access F_RMA submit. WeWa Business case being formulated

Discharge of conditions and variation of conditions to be submitted including foul drainage.

WeWa road business case to be confirmed.

A14 J10a – principal design and cost agreed for RGF bid.

EK Committee – conditions.

RMA’s and Full to EK Committee

Drainage strategy to be agreed.

Work on site clearance to start.

Government announcements in Autumn statement regarding RGF £30m A14 Jct 10a. RMA – Suds to be submitted.

A14 Jct 10a design principle  and cost agreed.

January 2014

February 2014

March 2014

April 2014

May 2014

June 2014

July 2014

August 2014

September 2014

October 2014

November 2014

Access points to start.

Drainage works started due to be completed Summer 2016

District Centre design discussions start

Discharge of detail RMA conditions

RMA – SUDS EK Committee

First house foundation started.

Jct 10 / Access F works start.

E/D – Access works completed. Potential RMA for Primary School.

Detailed application for A14 Jct 10a to be submitted

First house completed: Potentially.

Potential submit RMA - Employment E3 site

RMA for internal road links submitted

Jct 10 / Access F works completed. Phase 1 interim,

SUDS Attenuation Basin finished.

Discharge of conditions for internal roads

EK Committee – Primary school

Internal road construction starts.

December 2014

January 2015

February 2015

March 2015

April 2015

Potentially 50 houses completed from 3 development sites.

First Primary School starts on site. Ready September 2016